## Weekly report
(May.25 to May.29)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer study | Mooplayer OMX debug and EXOplayer study | 1. Debug [TF515PHIALLMTK01-16235(360852)] [CB] Most of the time ANR(media is not responding) is seen during CB playback and after that file cannot be read OSD is seen for any file playback. [Root Cause] In the multi-time playback,when end the playback of TS file,the vdec resource isn't release! [Solution] Has passed to the team of tsplayer to solve the issue.[100%] 2.Debug [TF515PHIALLMTK01-16093(359803)] [U+] Most of the time target crashes for the video playback. [Root Cause] According the log , it find that the audio compnent not shutdown in the previous playback . [Status] Wait for the available U+ device to analyze in the furture. [40%] 3. Write the outline about ExoPlayer Library.[100%] 4.Learn the interface of ExoPlayer for ContextExplorer.[20%-40%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(June.1 to June.5)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer Wrap | Mooplayer OMX debug and EXOplayer Wrap | 1.Debug [TF515PHIALLMTK01-16093(359803)] [U+] Most of the time target crashes for the video playback. [Root Cause] According the log , it find that the audio compnent not shutdown in the previous playback . [Status] Wait for the available U+ device to analyze in the furture. [40%] 2. Wrap the HLS interface about Exoplayer,set up the HLS test server.[60%] 3.Learn the interface of ExoPlayer for ContextExplorer.[40%-50%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(June.8 to June.12)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer Wrap | Mooplayer OMX debug and EXOplayer Wrap | 1.Debug [TF515PHIALLMTK01-16093(359803)] [U+] Most of the time target crashes for the video playback. [Root Cause] According the log , it find that the audio compnent not shutdown in the previous playback . [Status] Wait for the available U+ device to analyze in the furture. [40%] 2.Debug [TF515PHIALLMTK01-17356(365708)] [BBC][Catal][Regression]HLS Playback is not always restored after buffering [Status] On the version QM152E_R0.3.237.0,i can't reproduce the issue(30times),has passed to cofirm. [80%] 3. Wrap the HLS interface about Exoplayer,set up the HLS test server.[90%] 4.Learn the interface of ExoPlayer for ContextExplorer.[50%-55%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(June.15 to June.19)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer Wrap | Mooplayer OMX debug and EXOplayer Wrap | 1.Debug [TF515PHIALLMTK01-16093(359803)] [U+] Most of the time target crashes for the video playback. [Root Cause] According the log , it find that the audio compnent not shutdown in the previous playback . [Status] On the latest version,it didn't happend. Close. [100%] 2.Debug [TF515PHIALLMTK01-17120(364581)] [PTA][iOS][CB] Video Playback is not proper for Time laps Video. [Status] On the version QM152E_R0.3.245.0,i can't reproduce the issue,has passed to cofirm. [80%] 3.Learn the draft about HLS,prepare the PPT and share it.[100%] 4.Learn the interface of ExoPlayer for ContextExplorer.[50%-55%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )