## Weekly report(WK49)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
|  | 2015/6/23-2015/6/26 | week 26
2k15 EU Android | A | 1. Reading the code Dash's manifest parser function 2. fix the pr TF515PHIALLMTK01-18425 3. fix the pr TF515PHIALLMTK01-18602 | 1. Fix the PR 2. Read the code of ExoPlayer lib. 3. Learn about content explorer of DLNA. | 1. Learn about the content expoler code of VideoPlayerActivity, learn about android USBBradcaseReceiver, MainActivity[85%->90%] 2. Learn about Git of git fetch/git rebase/git reset [70%->75%] 3. Help check the PR: TF515PHIALLMTK01-18602 , a/v sync not OK. HardwareClock's STC updated no OK, need MTK to check[100%] 4. Fix the PR: TF515PHIALLMTK01-18425, the demo video stuck at the end of 2nd time finish playback. kWhatEOS not notify from driver. waiting for release next week[100%] 5. Learn about Dash's manifest, and read MediaPresentationDescripe.java to parse dash's manifest file. [100%] | Xianmei Liao | On schedule |  |  |  |  | 1