## Weekly report
(May.11 to May.15)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX debug and EXOplayer study | 1. Help to debug [TF515PHIALLMTK01-15109] [CB][Usability][Regression] TV shown blank screen while image or video playback after youtube playback followed by AV lost on tuner [Issue found] Do the command n.mute.q 0 0 when the screen blank. It show like the following: [ 3966.912681] Module = 0 (API_FORCE: AP) Invalid = 0x0 Delay conter = -1 And the mooplayer have snet the VideoPresence_notify(MediaProperty_ONVIDEOPRESENTCHANGED, true) to APP. This should be checked by APP firstly.[50%] 2. Debug OMX_VIDEO_CODECPARAMS notification is not coming from MTK and Get VideoGopBitrate always returns 0. [Solution]After adding the transfer interface in Aomxcomponent, the mooplayer can get the right VideoGopBitrate . The GetExtVideoGopQPInfo ,GetVideoDecoderInfo,IndexExtVideoProfile, getVideoHeadBitrateInfo also has added in Aomxcompnent.cpp.[100%] 3.Debug the system will be crash on LT sysbuid after play any video file. [Issue found] This is a mem map problem, MTK had fixed in EU project. Advice LT to test this issue after version 203.[100%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(May.4 to May.8)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1. Debug [Critical]when change the audio language ,the video will fastward for moment. [Issue found] After the MAT, mooplayer got the seek request for 9.81 sec, and the previous available I-Frame was at 4.96 seconds. But the hardwareclock not set the STC. The STC always in value before doing seek. [Solution] In the hardwareclock, it is to reset the STC after complete seek.[100%] 2.Debug the [TF515PHIALLMTK01-14938] Multiple Trick mode issues found during playback of contents from USB For: "011706__WebM_9Mbps_VP8_1920x1080_8Mbps_24FPS_VORBIS.webm". In the log , it found that the audio ready not notify from the audio driver after finnishing the trick. But the audio data have sent to the driver. This should be checked by MTK driver.[100%] 3. Help to debug [TF515PHIALLMTK01-15109] [CB][Usability][Regression] TV shown blank screen while image or video playback after youtube playback followed by AV lost on tuner [Issue found] Do the command n.mute.q 0 0 when the screen blank. It show like the following: [ 3966.912681] Module = 0 (API_FORCE: AP) Invalid = 0x0 Delay conter = -1 And the mooplayer have snet the VideoPresence_notify(MediaProperty_ONVIDEOPRESENTCHANGED, true) to APP. This should be checked by APP firstly.[50%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(April.19 to April.24)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1. Trace [DLNA/CB][Regression]No Audio on TV while music playback via DLNA server Issue found : In the attachment log , it found that the audio driver not update the STC. But it can’t reproduce in the latest code. Let the submitter to confirm and close.[100%] 2. Debug the following PRs: TF515PHIALLMTK01-14260 [PTA][Critical] Browser video to TV, TV reboot TF515PHIALLMTK01-13914 [Critical] Play .MP4 file in 6400series, TV reboot. Play .MP4 file in 5500series, TV picture abnormal TF515PHIALLMTK01-13450 [critical]exit demo me by press RC TV/exit key DUT reboot TF515PHIALLMTK01-13962 [Critical] 6400 once try to play Demo Me, TV reboot Issue found： In the hardware video decoder , it set a wrong value.After this fixing , all this PR can’t reproduce.[100%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(April.11 to April.17)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1. Debug [TF515PHIALLMTK01-11658] [SmartTV-OLS] Dash+ playready streaming happens with video freeze for every 2Secs. Issue found : Mooplayer read the video data from source almost take 3s . During the 3s, it is may always in downing the data. In the log , it find this case happened many times. The daily can check the attachment log. The video read from the source are so slow that the mooplayer will enter the buffering frequently. This should be checked by TPVision. [50%->100%] 2. Debug [Apple HLS]---Video screen freeze during playback of any video from Megogo V3 app Issue found: The hardware clock STC updated by audio decoder are jumping. Then the current position get from hardware clock not correct. So the mooplayer always enter buffering. After checking , this stream include many invalid audio pts. [Solution] If receiving the invalid pts in audio hardware decoder , it is to set the previous valid pts instead of this invalid ones. [100%] 3.Debug [Critical][LL]TV Fit to Screen error during play a 21:9 video Issue found: The driver had can notify the aspect ratio 21:9 to AOMX. AOMX had also notified this message to mooplayer. But mooplayer not deal with the 21:9 . After discuss with BLR, they will check whether support 21:9 aspect ratio. It not support the 21;9 in 2k14/2k15 marvell. [Solution] Not support 21：9 aspect ratio. When the mooplayer receive the 21:9 notified message , it is to set VIDEOPROPERTIES_ASPECTRATIO_UNKNOWN.[100%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(March.30 to April.3)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1. Debug [Codec]Video is going to pause for some sec and play for the webm file and macro blocks observed. Issue found: ‘Video is going to pause for some sec and play for the webm file’ have fixed by Xueyi’s solution. And the “macro blocks observed” also can found when play via VLC on PC. After letting TPVision to confirm and this PR have closed[100%] 2. Debug [TF515PHIALLMTK01-11658] [SmartTV-OLS] Dash+ playready streaming happens with video freeze for every 2Secs. Issue found : The STC will jump forward and backward sometimes. Thus mooplayer always enter buffering and resuem. This should checked by MTK audio driver.[50%] 3. Debug Hbbtv: Random crash in mediaserver. Issue found: Crash at: AOMXAudioDecoder.cpp:395 CHECK_EQ( static_cast<status_t>(OK),err) Because it can't get the IndexParamPortDefinition parameter from hardware. status_t err = mOMX->getParameter( mNode, OMX_IndexParamPortDefinition, &def, sizeof(def)); CHECK_EQ(static_cast<status_t>(OK), err); And it find that eADecDrvCreate error in hardware: 11-11 23:41:52.171 E/OMX_MtkAudioDecoder( 1028): eADecDrvCreate error The issue may be is the driver resource not release and re-allocate new resouce but not notify a fail message to AOMX then to mooplayer. MTK to check.[50%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(March.30 to April.3)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1. Debug [Codec]Video is going to pause for some sec and play for the webm file and macro blocks observed. Issue found: ‘Video is going to pause for some sec and play for the webm file’ have fixed by Xueyi’s solution. And the “macro blocks observed” also can found when play via VLC on PC. After letting TPVision to confirm and this PR have closed[100%] 2. Debug [TF515PHIALLMTK01-11658] [SmartTV-OLS] Dash+ playready streaming happens with video freeze for every 2Secs. Issue found : The STC will jump forward and backward sometimes. Thus mooplayer always enter buffering and resuem. This should checked by MTK audio driver.[50%] 3. Debug Hbbtv: Random crash in mediaserver. Issue found: Crash at: AOMXAudioDecoder.cpp:395 CHECK_EQ( static_cast<status_t>(OK),err) Because it can't get the IndexParamPortDefinition parameter from hardware. status_t err = mOMX->getParameter( mNode, OMX_IndexParamPortDefinition, &def, sizeof(def)); CHECK_EQ(static_cast<status_t>(OK), err); And it find that eADecDrvCreate error in hardware: 11-11 23:41:52.171 E/OMX_MtkAudioDecoder( 1028): eADecDrvCreate error The issue may be is the driver resource not release and re-allocate new resouce but not notify a fail message to AOMX then to mooplayer. MTK to check.[50%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(March.14 to March.20)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.Debug the video got frizzed after applying seek for specific wmv file through PMS. Have transfered TPVision and MTK to checck.[30%->60%] 2.Debug: [TF515PHIALLMTK01-11645] [Usability] [CB] [DLNA] Audio playback stops on playing the image file if music playback is happening in the background Issue found: The mooplayer send the data to the OMX/hardware normally, but do any change when run in background. This should be checked by APP.[100%] 3. Debug [MB][MusicPlaylist]:TV carsh is seen after pushing Music playlist to tV for the multiple time and zapping to next file from remote screen of PTA Issue found: The previous playback call the reset() during the prepare and not to release the hardware source. So the next playback to allocate the hardware source will fail. Solution: Not to do reset() when prepare in mooplayer.[100%] 4.1.Debug Multiple issues are observed for Specific MKV files through DLNA/USB. Issues found: The audio data can’t send to the driver after do seek then the OMX buffer full. The mooplayer can’t sent more data to omx. This should be check by MTK driver.[100%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(March.7 to March.13)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.Debug frames are going very fast for few seconds on applying FR seek for 000007__MPEG-PS_7Mbps_MPEG-2_720x480_6Mbps_29.97FPS_AC3.VOB file.Have modified some code in the ffmpegextractor.cpp and test ok in local. The changed code have sent to TPvision for further confriming.closed.[80%->100%] 2.Debug fast-backward Trick mode on Time Seek server results in ANR: IFrame seek hangs due to OMX state change notification is not received when the AOMX tries to perform the state change, the driver not notify the flush complete.This should be checked by MTK.fixed in driver[50%->100%] 3.Trace video got frezzed after applying seek for specific wmv file through PMS: the driver not notify the display message when the last seek.This should be debugged by MTK.This issue fixed ,but have another exist issue.This can be closed[30%->100%] 4.Trace video Freeze happen after applying seek for a particular file mp4 file.Issues found: - AV sync issue after seek – seems h/w clock not set correctly - Audio flush complete notification did not reach to mooplayer.fixed[30%->100%] 5.Debug the video got frizzed after applying seek for specific wmv file through PMS. Issues found: After provided the patch to TPVision for testing, issue fixed when tested in USB, however, some issue still exists in DLNA. In the log, I found that the mooplayer pause after "Seek-Resume", the TPvision will check this cause.[30%] 6. Debug trickmodes are not smooth. Issues found: a. The mooplayer push the same data both of trick -- tpvision will check from app to mooplayer b. The mooplayer sometimes send the data delay sec when do the trick -- tpvision will check this I will continue to check this issue with MTK and TPvision.[30%] 7. Trace [Playready]----Video getting freezed sometime when trick modes performed during playback: Issues found: The MTK driver not notify “Iframe display” event, maybe have some problem in MTK driver. Have transfer this issue to MTK, they will analyses in the driver.[30%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(March.2 to March.6)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.Debug the Specific .Webm file seek and trickmodes are not working properly and find out the hardclock notify a incorrect value when do the seek..The driver not update STC. This should be confirmed by MTK driver first.Have tansfered to MTK.[30%][blocking in MTK] 2.Debug frames are going very fast for few seconds on applying FR seek for 000007__MPEG-PS_7Mbps_MPEG-2_720x480_6Mbps_29.97FPS_AC3.VOB file.Have modified some code in the ffmpegextractor.cpp and test ok in local. The changed code have sent to TPvision for further confriming.[30%->80%] 3.Debug fast-backward Trick mode on Time Seek server results in ANR: IFrame seek hangs due to OMX state change notification is not received when the AOMX tries to perform the state change, the driver not notify the flush complete.This should be checked by MTK.[50%] 4.Trace video got frezzed after applying seek for specific wmv file through PMS: the driver not notify the display message when the last seek.This should be debugged by MTK[30%] 5.Trace video Freeze happen after applying seek for a particular file mp4 file.Issues found: - AV sync issue after seek – seems h/w clock not set correctly - Audio flush complete notification did not reach to mooplayer.[30%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(February.2 to February.6)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.Debug the Specific .Webm file seek and trickmodes are not working properly and find out the hardclock notify a incorrect value when do the seek..The driver not update STC. This should be confirmed by MTK driver first.Have tansfered to MTK.[30%][blocking in MTK] 2.debug the Playback of any content gets stuck at the first frame after a specific steps of operation and find out the clock component shutdown not send to hardwareclock. fixed after MTK driver can notify the "EOS" to mooplayer.[50%->100%] 3.Trace video hang observed after applying seek or trick mode for .wmv file. It find this .wmv file have less Ifame. So it may send the same data to driver when the step of trick is small. After set the pts = dts in asfdec.c , this bug fixed.[30%->100%] 4.Trace playback struck and plays after applying play-pause and seek. Fixed some code in hardwareclock[30%->100%] 5.Debug frames are going very fast for few seconds on applying FR seek for 000007__MPEG-PS_7Mbps_MPEG-2_720x480_6Mbps_29.97FPS_AC3.VOB file.[30%] tarnsfered to xiangbin for debug | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(February.2 to February.6)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.Debug the Specific .Webm file seek and trickmodes are not working properly and find out the hardclock notify a incorrect value when do the seek..The driver not update STC. This should be confirmed by MTK driver first.[30%][blocking in MTK] 2.debug the Playback of any content gets stuck at the first frame after a specific steps of operation and find out the clock component shutdown not send to hardwareclock. This should be traced further[30%->50%] 3.Trace video hang observed after applying seek or trick mode for .wmv file. It find this .wmv file have less Ifame. So it may send the same data to driver when the step of trick is small.[30%] 4.Trace playback struck and plays after applying play-pause and seek. [30%] 5.Debug frames are going very fast for few seconds on applying FR seek for 000007__MPEG-PS_7Mbps_MPEG-2_720x480_6Mbps_29.97FPS_AC3.VOB file.[30%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(January.26 to January.30)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.introduce the basic knowledge of multimedia to the newcomer[100%] 2.help MTK to debug the whenever play marlin MS3 MPEG4 AVC content, the streaming get stops after 6 Secs[100%] 3.Debug the Specific .Webm file seek and trickmodes are not working properly and find out the hardclock notify a incorrect value when do the seek..The driver not update STC. This should be confirmed by MTK driver first.[30%] 4.debug the Playback of any content gets stuck at the first frame after a specific steps of operation and find out the clock component shutdown not send to hardwareclock. This should be traced further[30%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(January.19 to January.24)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.Debug resume takes nearly 1 to 2secs to start he playback – it is not an acceptable user experience and also video frame flickers after doing Resume playback:find out it take a long time to do next trick in APK, need check by TPVision,transfer to TPvision.[50%->100%] 2.Debug when Fastforward action reaches at the end of the file,the playback running time displays more than file duration time.We don't have the key,the BBCiplayer can't play in XM.It can't repeat this issues.It found that the root cause is the driver not notify the "EOS". It haa fixed by mtk[10%->100%] 3. Handing the invalid PTS in hardware and sending the patch to BLR[50%->100%]. 4.Trace the video will freeze when do seek at the end of file. And it find that the hardware can’t received the data after seek.[30%->100%] | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(January.12 to January.17)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.Debug video frame is delayed while doing apple HLs playback(the invalid pts send to the driver, need fix in mtk hardware) (100%) 2.Debug resume takes nearly 1 to 2secs to start he playback – it is not an acceptable user experience and also video frame flickers after doing Resume playback:find out it take a long time to do next trick in APK, need check by TPVision(10%->50%) 3.Debug when Fastforward action reaches at the end of the file,the playback running time displays more than file duration time.We don't have the key,the BBCiplayer can't play in XM.It can't repeat this issues.(10%) 4. Handing the invalid PTS in hardware and sending the patch to BLR(50%). 5.Trace the video will freeze when do seek at the end of file. And it find that the hardware can’t received the data after seek.(30%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(January.3 to January.9)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension and debug | Mooplayer OMX Extension and debug | 1.Trace playback will be hung and the playback screen will be freezed if will do multiple resumes to the video playback.(100%) 2. Fixed the first time Pause-Play is not working for all files.(100%) 3. Fixed Play-pause multiple times get stuck in A/V files with DTS-HD audio.(100%) 4.Debug video frame is delayed while doing apple HLs playback(10%) 5.Debug resume takes nearly 1 to 2secs to start he playback – it is not an acceptable user experience and also video frame flickers after doing Resume playback(10%) 6.Debug when Fastforward action reaches at the end of the file,the playback running time displays more than file duration time(10%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(December.22 to December.26)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.Fixing the hevc codec not support,the root cause is that the hevc header not parse.But it displays dimness the when display Size > 1920 * 1088. This should be check by MTK.MTK have not any upgrade.(fixed by mtk) 2. the normal seek trick mode still have one issues: sometimes do the forward then play ,the video would freeze.This issues will debug with MTK forward(100%). 3. Trace no AV is seen during playback of HEVC contents for .MKV files. The root cause is video been muted by APP (Maybe display region not set).(transfer to TPvision) 4.Debug a MP4 file can’t play. And found that a frame size is larger than the empty buffer size,the driver haven’t recompose this frame.(100%) 5.Trace playback will be hung and the playback screen will be freezed if will do multiple resumes to the video playback.(10%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(December.15 to December.19)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.Fixing the hevc codec not support,the root cause is that the hevc header not parse.But it displays dimness the when display Size > 1920 * 1088. This should be check by MTK.MTK have not any upgrade.(blocking) 2.Debug the Playback stucks at the end of the file if apply seek multiple times for all AV files through USB/DLNA and found that it would send a “EOS” flag to hardware at the end the file. If it want to do the seek again, the hardware should clear the “EOS” flag.(50%)(transfer to Fenton ) 3.fixed the trick mode related issuses: a.“Trick mode + stop” and play again doesn’t start(100%). b."Trick mode->EOS" can't exit(100%) . 4.Redesign the Iframe trick mode: use the normal seek replaced with the seek accuary.Coding and test the new trick mode ,the basic function has finished. The img and patch have sent to BLR.(100%) 5. the normal seek trick mode still have one issues: sometimes do the forward then play ,the video would freeze.This issues will debug with MTK forward(30%). | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(December.8 to December.12)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.Implement of the trick mode via the IFrameSeekto: integrated the patch provided by MTK,the mooplayer have receviced the "Displayed event",but only do several times, and freeze.Fixed this issuse with MTK.(100% ) 2.Fixing the hevc codec not support,the root cause is that the hevc header not parse.But it displays dimness the when display Size > 1920 * 1088. This should be check by MTK.MTK have not any upgrade.(60%) 3.Debug the Playback stucks at the end of the file if apply seek multiple times for all AV files through USB/DLNA and found that it would send a “EOS” flag to hardware at the end the file. If it want to do the seek again, the hardware should clear the “EOS” flag.(50%) 4. Help tpvision to debug : 1) play any file (playback starts) (OK) 2) Pause the playback (pauses the playback) (OK) 3) Stop the playback (Stops the playback) (OK) 4) play any other file (playback doesn't start) (NOK) and found that the video and audio data have sent to the driver but the A/V can’t come out. Fixed in hardware.(100%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(December.1 to December.5)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.Implement of the trick mode via the IFrameSeekto: integrated the patch provided by MTK,the mooplayer have receviced the "Displayed event",but only do several times, and freeze.Waiting for TPvision and MTK reach a consensus on the new proposal (70%->75% ) 2.Fixing the hevc codec not support,the root cause is that the hevc header not parse.But it displays dimness the when display Size > 1920 * 1088. This should be check by MTK.MTK have not any upgrade.(60%) 3. Attending the meeting about the Iframe based trick mode with MTK and TPVision for three days. 4.Debug the Playback stucks at the end of the file if apply seek multiple times for all AV files through USB/DLNA and found that it would send a “EOS” flag to hardware at the end the file. If it want to do the seek again, the hardware should clear the “EOS” flag.(50%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(November.24 to November.28)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.Implement of the trick mode via the IFrameSeekto: integrated the patch provided by MTK,the mooplayer have receviced the "Displayed event",but only do several times, and freeze.This issues should be debug with MTK(70%->75% ) 2.Fixing the hevc codec not support,the root cause is that the hevc header not parse.But it displays dimness the when display Size > 1920 * 1088. This should be check by MTK.MTK have not any upgrade.(60%) 3.Debug the VC1 video codec can't play,this have transferred to Xianmei(10%)(closed) 4.Debug the MAT can't work(100%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(November.17 to November.21)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.Implement of the trick mode via the IFrameSeekto: integrated the patch provided by MTK,but found that “Displayed event” is not getting notified at “HardwareVideoRenderer.cpp” itself in some Container(mkv,mp4…).This issues should be debug with MTK(60%->70% ) 2.Fixing the hevc codec not support,the root cause is that the hevc header not parse.But it displays dimness the when display Size > 1920 * 1088. This should be check by MTK.(60%) 3.Debug the VC1 video codec can't play(10%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(November.10 to November.14)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.implement of the trick mode via the IFrameSeekto :Delete the Audio decoder and rebuild the Audio decoder has finished. But now the disconnect audio render and clock then re-connect not work,the Audio data can’t send the to OMX. These interface have provided by MTK.(60%->70% ) 2.Help MTK to debug the continuous play pause from RC makes the progress bar head to jump to beginning. The root cause is the HardwareClock notify a “0” Timestamp sometimes, this issuse has fixed.(100%) 3.Merged the MAT to the ontop of latest mooplayer changes and test passed.(100%) 4.Modifid the related code that the mooPlayer can play the mediafile via fd path(100%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(October.27 to November.7)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.implement of the trick mode via the IFrameSeekto :Delete the Audio decoder and rebuild the Audio decoder has finished. But now the disconnect audio render and clock then re-connect not work,the Audio data can’t send the to OMX. These interface have provided by MTK.(50%->60 ) 2.Study the TVmediaplayer.java which replaced with the primary GTVmediaplayer.Java(100%) 3.help MTK to debug the WMA have noise and the WMV can’t play(100%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(October.20 to October.24)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.implement of the switch audio on FB4.1:The sequence of MAT has implemented on the mooplayer and AOMXComponent .But the OMXAudio component do not send the command to required the data from mooplayer.The MTK has provied the inteface,and the MAT is ok.(100%) 2.implement of the trick mode via the IFrameSeekto :Delete the Audio decoder and rebuild the Audio decoder has finished. But now the disconnect audio render and clock then re-connect not work,the Audio data can’t send the to OMX. These interface should provided by MTK.(40->50% block by mtk) 3.Debug Stop and Play – Doesn’t work (while playing the 1st file do Stop(enters into the browser screen) then try playback of the next file) .The root cause is that the contentexploer.apk call the stop and reset at the same time. It cause some conflict in MTK’OMX.(100%) 4.Study the TVmediaplayer.java which replaced with the primary GTVmediaplayer.Java(50%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(October.13 to October.17)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.implement of the switch audio on FB4.1:The sequence of MAT has implemented on the mooplayer and AOMXComponent .But the OMXAudio component do not send the command to required the data from mooplayer.These need debug by MTK,so the MAT is blocked.(60% block by mtk ) 2.implement of the trick mode via the IFrameSeekto :Delete the Audio decoder and rebuild the Audio decoder has finished. But now the disconnect audio render and clock then re-connect not work,the Audio data can’t send the to OMX. These interface should provided by MTK.(40% block by mtk) 3.Debug Stop and Play – Doesn’t work (while playing the 1st file do Stop(enters into the browser screen) then try playback of the next file) (30%) 4.Study the TVmediaplayer.java which replaced with the primary GTVmediaplayer.Java(50%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(Septemper.29 to October.11)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX Extension | Mooplayer OMX Extension | 1.help MTk to debug the terrible noise in FB4.1.(100%) 2.confirm the PCM codec on FB4.1 (100%) 3.implement of the switch audio on FB4.1(30%->50%) 4.implement of the trick mode via the IFrameSeekto(30%) | YouMing.Huang | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(Septemper.22 to Septemper.26)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer porting to L and OMX Extension | Mooplayer porting to L and OMX Extension | 1.help MTk to debug the terrible noise in FB4.1.(50%->60%) 2.help TPVision to debug the media file can't play on FB4.1(100%) 3.confirm the PCM codec on FB4.1 (30%) 4.confirm the Select track on FB4.1(30%) 5.one day on the trip from BLR to XM | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(Septemper.15 to Septemper.19)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer porting to L and OMX Extension | Mooplayer porting to L and OMX Extension | 1.Debug the apk crash when select track(Done:100%) 2.help TPVison to debug the FW5’s APK can’t work in their platform(Done:100%) 3.Debug when play any media files with audio&video using HW decode with MooPlayer, audio output terrible noise.The root cause is MTK. 4.Debug When use android default music player with SW decode, it will no audio output. The root cause is MTK. 5.help tpvision to debug the Resourcemanger Service can’t set up in their merged code.(Done:100%) 6.help MTk to debug the terrible noise in FB4.1.(Done:50%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(Septemper.9 to Septemper.13)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer porting to L and OMX Extension | Mooplayer porting to L and OMX Extension | 1.study the stagefrightplayer’ DRM(Done:40%) 2.Debug the apk crash when select track(Done:40%) 3.help TPVison to debug the FW5’s APK can’t work in their platform(Done:50%) 4.porting the Select Track code provided by TPVision to the Android_l and build pass(100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(Septemper.1 to Septemper.5)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer porting to L and OMX Extension | Mooplayer porting to L and OMX Extension | 1.set up the Android_L environment in our server,and the porting code build success(Done:100%) 2.Study the flow of mediaplayer's setdatasource from the Java to frameworks in Android_L and find the different between the JB and L(Done:100%) 3.study the TimedEventQueue-event : the event new ,post and receive(Done:100%) 4.study the stagefrightplayer’ DRM(Done:30%) 5.Debug the apk crash when select track(Done:30%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(August.25 to August.29)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer porting to L and OMX Extension | Mooplayer porting to L and OMX Extension | 1. integration new tarball tag48 and run ok and help mtk to porting ffmpeg(Done:100%) 2.Debug the app crash when selectTrack:The GtvClassBridge::TrackInfo throw an IllegalAccessError.(Done:100%) 3.Debug the mooplayer return “error” when set stop:the HardwareVideoDecoder return “error”,this issues should be debug by mtk.(Done:100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(August.18 to August.22)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer porting to L and OMX Extension | Mooplayer porting to L and OMX Extension | 1.Set up the Android_L hardware run environment in MTk(Done:100%) 2.get the MTK released Android_L code and modify the setting of ubuntu and build the Android_L code then passed(Done:100%) 3.debug the APK cash and found out the root cause in Android_L(Done:100%) 4.Set up the full environment , the partial media file can playback via mooplayer on Android_L(Done:100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(August.11 to August.15)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer | Mooplayer porting to L and OMX Extension | 1.review the data flow of select track both on the mooplayer and Stagefrightplayer(Done:100%) 2. Design the mooplayer’s Seek accuracy from the mooplayer to omx and set cmd to omx(Done:100%) 3.porting the code about the trick mode from Marvell to MTK platform(Done:100%) 4.Design the trick mode of mooplayer and discuss the detail with MTk(Done:60%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(August.4 to August.8)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer | debug the mooplayer | Attending the meeting with MTK and TPVison,and discuss the following issues: 1.the Implementation of TrickMode (IFrame ,seek accuracy) 2.Audio and Video Properties incl.Video Presence,first frame displayed event,profile and level ,FPS ect. 3. A/V Sync(Audio master , System master and freerun) 4.DRM – License/Key acquisition using classic DRM framework, playback using libCrypto. 5. The data flow of widevine in mooplayer 6. WMDRM : RC4 decryption 7.Codec change or MAT change 8. Passing of DSI for different Codecs 9. UHD/HEVC playback via OMX 10. Pipeline construction,tunnelled Video and Audio Rendering 11. Seamless swiching of Audio/video acorss the representation adoptive streaming | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(July.28 to August.1)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer | debug the mooplayer | 1.review the data flow of mooPlayer’s selecttrack(Done :100%) 2.debug the surface black when selcect the audio track(Done:30%) 3.Study the StagefrightPlayer: study the data flow of setdatasource 、prepareAsync and the principle of TimedEventQueue(Done:100%) 4. Attend the mooplayer meeting with MTK： a.the OMX codec info extension b. OpenMax IL extention to support trick modes c. Switch the audio and subtitle | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(July.21 to July.25)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer | debug the mooplayer | 1.Debug the media file can’t play when the audio's codec is AC3 but vedio's codec is supported(Done:70%). 2.Debug the MKV file can’t seek accurately(Done:100%). 3.Analysis the data flow of only audio play via StagefrightPlayer(Done:100%). 4.review the Platform_Requirements_MTK2k15_w1428 4_modified(Done 100%). | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(July.14 to July.18)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer | debug the mooplayer | 1.Debug the vedio freeze after seeking,when play the ASF file(Done:100%) 2.Debug the media file can’t play when the audio's codec is AC3 but vedio's codec is supported(Done:70%) 3.Study the use of Gerrit and config the parameter to download and upload the code (Done :100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(July.7 to July.11)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study DASH related code | debug the mooplayer | 1. Analyse the data flow of transporting the container’s code information from FFmpegExtractor to OMX and try to add the more related info (Done:100%) 2.Debug the mkv can’t play smoothly when setting “SEEK”（Done:100%） 3.Debug the vedio freeze after seeking,when play the ASF file(Done:30%) 4.Study the format of Wave(Done:100%) 5.Add the necessay parameter of DTS to OMX (Done:100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(June.30 to July.4)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study DASH related code | debug the mooplayer and study DASH related code | 1. test the function of dash and debug the dash can’t play(Done:50%) 2. Analyse the data flow of transporting the container’s code information from FFmpegExtractor to OMX and try to add the more related info (Done:50%) 3.Debug the mkv can’t play smoothly when setting “SEEK”（Done:50%） | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(June.23 to June.27)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study DASH related code | debug the mooplayer and study DASH related code | 1.Fix the mooPlayer can't replay when set "second STOP"(Done:100%) 2.Debug the mooPlayer play fast forward after set "STOP"(Done:100%) 3. test the function of dash and debug the dash can’t play(Done:40%) 4.Fix the mkv replay would always “Pause” and “Resume” when setting “STOP”(Done:100%) 5. Analyse the data flow of transporting the container’s code information from FFmpegExtractor to OMX and try to add the more related info (Done:40%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(June.16 to June.20)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study DASH related code | debug the mooplayer and study DASH related code | 1.Debug the mooPlayer can't replay when set "second STOP"(Done:50%) 2.Debug the mooPlayer play fast forward after set "STOP"(Done:50%) 3. test the function of dash and debug the dash can’t play(Done:30%) 4.merge the Fixed bug’s code to Tag55 and update to Git server(Done:100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(June.9 to June.13)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study DASH related code | debug the mooplayer and study DASH related code | 1.Debug the mooPlayer vedio can’t replay after Set Stop(Done:100%) 2. Study the AOMXComponent and AOMXProxy(Done:100%) 3.Fix The HLS can't play(Done:100%) 4.Debug the mooPlayer can't replay when set "second STOP"(Done:30%) 5.Debug the mooPlayer play fast forward after set "STOP"(Done:30%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(June.3 to June.6)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study DASH related code | debug the mooplayer and study DASH related code | 1.Debug the the mooPlayer vedio can’t replay after Set Stop(Done:60%) 2. Study the AOMXComponent and AOMXProxy(Done:60%) 3.Test mkv/hls and report bugs (100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(May.26 to May.30)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study DASH related code | debug the mooplayer and study DASH related code | 1．Review the Git and write a list about how to add the SSH Key(Done：100%) 2. Review the data flow of mooPlayer from Java->JNI->native(Done:100%) 3.Debug the the mooPlayer vedio can’t replay after Set Stop(Done:50%) 4. Study the AOMXComponent and AOMXProxy(Done:50%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(May.19 to May.23)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study DASH specification | debug the mooplayer and study DASH related code | 1.modfied and debug the merged code on the MTK tag45(Done:100%) 2.test the function of mooPlayer on the merged code(Done:100%) 3.Debug the CRs that the Mooplayer can’t play smoothly on the merged code(Done:100%) 4.merged the MTK tag45 code to 2k15tpvisioneu_mtk(Done 100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(May.12 to May.16)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | merge and debug the mooplayer | debug the mooplayer and study DASH specification | 1.modfied and debug the merged code on the MTK tag45(Done:60%) 2.test the function of mooPlayer on the merged code(Done:60%) 3.Debug the CRs that the Mooplayer can’t play smoothly on the merged code(Done:50%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(May.4 to May.9)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | merge and debug the mooplayer | merge and debug the mooplayer | 1.merge Marvell1.85's mooPlayer related code to MTK tag45(Done:100%) 2.modfied and debug the merged code on the MTK tag45(Done:30%) 3.test the function of mooPlayer on the merged code(Done:30%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(April.28 to April.30)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer and study OMX | debug the mooplayer and study OMX | 1.study the specification of DASH(60%) 2.test the function of MooPlayer on the new code with Tag44 and add log to trace the flow of MooPlayer’s Seek(Done:100%) 3.test the function of MooPlayer based on the Tag45(Done:100%) 4. wrirte MooPlyer Design Doucment about DRM(Done:100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(April.21 to April.25)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | debug the mooplayer | debug the mooplayer and study OMX | 1. study TS specification(Done:100%) 2.study the specification of DASH(50%) 3.test the function of MooPlayer on the new code with Tag44 and add log to trace the flow of MooPlayer’s Seek(Done:70%) 4.debug the get_CurrentPosition is incorrect when GtvMediaPlayer call(Done:100%) | YouMing.Huang | On schedule | study and debug(With Schedule) | study and dubug ( next Week )
(April.14 to April.18)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | study the ffmpeg and study HLS | debug the mooplayer | 1.study the HLS based on mooPlayer (Done:100%) 2.write a PPT about HLS(Done:100%) 3. Set up a test environment of HLS and test the function of HLS 4. study TS specification(Done:80%) | YouMing.Huang | On schedule | study (With Schedule) | study ( next Week )
(April.7 to April.11)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | study the ffmpeg :matroska and asf study HLS | study the ffmpeg and study HLS | 1.study the Matroskadec.cpp: matroska_probe,matroska_read_header , matroska_read_packet and writing doucements(Done:100%) 2.study ASFdec and writing doucements(Done:100%) 3.study the HLS specification(Done:100%) 4.study the HLS based on mooPlayer(Done:60%) | YouMing.Huang | On schedule | study (With Schedule) | study ( next Week )
(March.31 to April.4)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | study the ffmpeg :matroska,mp3,asf | study the ffmpeg :matroska and masf study HLS | 1.study the Architecture of ffmpeg: FFMPEG format probe flow and stream parse flow (Done:100%) 2.study the Matroskadec.cpp: matroska_probe,matroska_read_header , matroska_read_packet(Done:100%)and writing doucements(Done:80%) 3.study mp3dec and writing docements(Done:100%) 4.study ASFdec(Done:50%) | YouMing.Huang | On schedule | study (With Schedule) | study ( next Week )
(March.24 to March.28)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | study and fix the FFmpeg | study the ffmpeg :matroska,mp3,asf | 1.study the Architecture of ffmpeg: FFMPEG format probe flow and stream parse flow (Done:60%) 2.test MKV file with the ffmpeg(Done:100%) 3.study the Matroskadec.cpp: matroska_probe,matroska_read_header and matroska_read_packet(Done:50%) | YouMing.Huang | On schedule | study (With Schedule) | study ( next Week )
(March.17 to March.21)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | study the ASF and FFmpeg | study and fix the FFmpeg | 1.study ASF specification(Done:100%) 2.study the Architecture of ffmpeg(Done:40%) 3. help to fix the issue that TVPlayer will crash when run testAPP(Done:50%) | YouMing.Huang | On schedule | study (With Schedule) | study ( next Week )