## Weekly report(WK10)
(July.14 to July.18)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Check Media_compatibility_test_result, test avi, es, avs and other documents, collect the codecs that currently supported.[done:50%] 2.Study avi file format.[done: 100%] 3.Solve various problems during using XMIC Gerrit server.[done:100%] 4.Review FFMPEG Design Documents;[done:30%] 5.Coding AIFFExtractor under the framework of stagefright.[done:50%] | xiangbin.feng | On schedule |  |  |  |  | 1
(July.21 to July.25)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Analysis the problem that the avi can't play when its codec is MP4V2.[done:100%] 2.Review Platform_Requirements_MTK2k15_modified[done:100%] 3.Server Maintenance.[done: 100%] 4.Review FFMPEG Design Documents.[done:50%] 5.Coding AIFFExtractor under the framework of stagefright.[done:100%] 6.Debug AIFFExtractor module.[done:30%] | xiangbin.feng | On schedule |  |  |  |  | 1
(July.28 to August.01)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Review Platform_Requirements_MTK2k15_w1429 4_OMX_IL and grasp how to implement it.[done:100%] 2.Server Maintenance.[done: 100%] 3.Review FFMPEG Design Documents.[done:70%] 4.Debug AIFFExtractor module.[done:90%] 5.Review stagefright flow.[done:100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(August.04 to August.08)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Analysis OMX_IL extension requirements.[done:100%] 2.Server Maintenance.[done: 100%] 3.Coding to support MP1 codectype extension.[done:80%] 4.Study RM specification and analysis RealMedia File Format.[done:60%] 5.Test Real Audio file and analysis logs to ensure that ra media file go through mooplayer or stagefright.[done:100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(August.11 to August.15)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Coding to support MP1 codectype extension.[done:100%] 2.Study RM specification and analysis RealMedia File Format.[done:100%] 3.Server Maintenance.[done: 100%] 4.Coding to support DTS/AAC/PCM codectype extension.[done:100%] 5.Coding to support COOK codectype extension.[done:90%] | xiangbin.feng | On schedule |  |  |  |  | 1
(August.18 to August.22)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Coding to support COOK codectype extension.[done:100%] 2.Server Maintenance.[done: 100%] 3.Compile and test audio codec expanded code, fix the problem during compiling.[done:100%] 4.Test Android L code, resolve the relevant problem.[done:100%] 5.Intergration and test the project after the open OMX extended.[done:100%] 6.Review resource manager module.[done:70%] | xiangbin.feng | On schedule |  |  |  |  | 1
(August.25 to August.29)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Review resource manager module.[done:100%] 2.Server Maintenance.[done: 100%] 3.Encapsulated API of resource manager module for video main/sub path select.[done:100%] 4.Test what codecs currently were supported.[done:100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(September.01 to September.05)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Merge ffmpeg module to Tag28 and complie;[100%] 2.Server Maintenance.[100%] 3. Debug that avi can’t play after seek to 0.[0->30%] 4.Test audio only file pause and seek after add prAdecOmx->fgRenderTrigger = FALSE.[100%] 5.Debug that the position of f4v file doesn’t stop after end of stream;[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(September.09 to September.13)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1. Repo init 、sync and compile FB4 code.[100%] 2.Server Maintenance.[100%] 3.Test avi、flv、mp4、mkv and other media file on the Android L platform.[0->30%] 4.Check and review codectype extended code.[100%] 5.Analysis the issue that 006639 and 001363 media file can’t play.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(September.15 to September.19)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1. Merge the extension of CONN.COPENMAX.0 and CONN.OPENMAX.2 to FB4.1 with xianmei.liao.[100%] 2.Server Maintenance.[100%] 3.Test avi、flv、mp4、mkv and other media file on the Android L platform.[30%->60%] 4.Debug the 000032 and 黄健翔激情解说高清收藏版.rm media file can’t play.[100%] 5.Sync and compile FB4.1 code.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(September.22 to September.26)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1. Penetrating and summarize the related documents about main or sub video path select API.[100%] 2.Server Maintenance.[100%] 3.Test avi、flv、mp4、mkv and other media file on the Android L platform.[60%->100%] 4.Sync and compile FB5 code and review Trick Mode..[100%] 5.Fix internal compiler error.[100%] 6.Debug that avi can’t play after seek to 0.[pendding] | xiangbin.feng | On schedule |  |  |  |  | 1
(October.08 to October.11)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1. Analyse and share the use case that how to use MediaPlayer.h to configure MooPlayer using sub path for media playback;.[100%] 2.Server Maintenance.[100%] 3.Debug DTS audio codecs are not working, the issue maybe caused that the code doesn’t add param.nEndian = true;.[0%->80%] 4.Flash the newest FB5 pkg, debug the bug that Play a M4A file and later TV crashes and hangs. And I check the log and find FIFO print is flooding the console and later goes and crashes. This is the reason I find that causes the crash issue.[100%] 5.Analyse PCM support problem with Xianmei.[100%] 6.Debug that avi can’t play after seek to 0.[pendding] | xiangbin.feng | On schedule |  |  |  |  | 1
(October.13 to October.17)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [0%->20%] 2.Server Maintenance.[100%] 3.Debug DTS audio codecs are not working, the issue maybe caused that the code doesn’t add param.nEndian = true;.[80%->85%] 4.Debug the issue that the app fail to get music covers、the first frame of video 、singer and album name.[100%] 5.Debug that avi can’t play after seek to 0.[pendding] | xiangbin.feng | On schedule |  |  |  |  | 1
(October.20 to October.24)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [20%->50%] 2.Server Maintenance.[100%] 3.Debug DTS audio codecs are not working, the issue maybe caused that the code doesn’t add param.nEndian = true;.[85%->100%] 4.Test Game Controller on TV with 5593 EU platform.[100%] 5.Flash the newest PKG and test kinds of media files on 5593 EU platform.[0%->50%] 6. Merge the OMX Extened codes from Tag28 to FB4.1.[100%] 7.Debug that avi can’t play after seek to 0.[pendding] | xiangbin.feng | On schedule |  |  |  |  | 1
(October.27 to October.31)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [50%->60%] 2.Server Maintenance.[100%] 3.Flash the newest PKG and test kinds of media files on 5593 EU platform.[50%->100%] 4.To extend audio/video CODINGEXTTYPE、related structures and interfaces for the newly added codecs and events. [0%->60%] 5.set up http and DLNA test environment.[0%->70%] 6.Debug that avi can’t play after seek to 0.[pendding] | xiangbin.feng | On schedule |  |  |  |  | 1
(November.03 to November.07)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [60%->75%] 2.Server Maintenance.[100%] 3.Review WMV module to solve the mapping problem which causes WMV play unsuccessfully.[100%] 4.To extend audio/video CODINGEXTTYPE、related structures and interfaces for the newly added codecs and events. [60%->80%] 5.set up http and DLNA test environment.[100%] 6.Debug WMA file plays unsuccessfully.[100%] 7.Review OMX Extend list to confirm whether the feature completed or not.[50%] 8.Debug that avi can’t play after seek to 0.[pendding] | xiangbin.feng | On schedule |  |  |  |  | 1
(November.10 to November.14)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [75%->80%] 2.Server Maintenance.[100%] 3.To extend audio/video CODINGEXTTYPE、related structures and interfaces for the newly added codecs and events. [80%->85%] 4.Review OMX Extend list to confirm whether the feature completed or not.[50%->70%] 5.Debug API’s and related event which are available to configure high and low water marking are not working.[100%] 6.Review hardware code which is related to OMX.[30%] 7.Debug that avi can’t play after seek to 0.[pendding] | xiangbin.feng | On schedule |  |  |  |  | 1
(November.17 to November.21)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [80%->85%] 2.Server Maintenance.[100%] 3.To extend audio/video CODINGEXTTYPE、related structures and interfaces for the newly added codecs and events. [100%] 4.Review OMX Extend list to confirm whether the feature completed or not.[100%] 5.Review hardware code which is related to OMX.[30->50%] 6.Add related code to support WMV codec.[100%] 7.Debug that avi can’t play after seek to 0.[pendding] | xiangbin.feng | On schedule |  |  |  |  | 1
(November.24 to November.28)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [85%->pendding] 2.Server Maintenance.[100%] 3.Review hardware code which is related to OMX.[100%] 4.Test the wmv input data and add the start code to the frame.[0%->80%] 5.Debug that avi can’t play after seek to 0.[fix] | xiangbin.feng | On schedule |  |  |  |  | 1
(December.01 to December.05)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [85%->pendding] 2.Server Maintenance.[100%] 3.Test the wmv input data and add the start code to the frame.[100%] 4.Fix WMV files are not playing through USB.[100%] 5.Fix ASF file are not playing through USB.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(December.08 to December.12)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [85%->pendding] 2.Server Maintenance.[100%] 3.Analyze the VC-1 files are not playing issue, and add and integration the related code.[100%] 4.Help to reproduce the Demo me issue.[100%] 5.Analyze the wmv&asf can’t be played in tpvision, add the related code and find there are some integration problem.[100%] 6.Debug some DTS files can be played.[30%] | xiangbin.feng | On schedule |  |  |  |  | 1
(December.15 to December.19)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [85%->pendding] 2.Server Maintenance.[100%] 3.Debug some DTS files can be played.[30%->50%] 4.Debug the issue that the artist name of some mp3 files display illegible.[100%] 5.Extend and implement the getPeerVideoHeadBitrate() interface.[100%] 6.Analyze the board crash issue in CN platform.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(December.22 to December.26)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [85%->pendding] 2.Server Maintenance.[100%] 3.Debug some DTS files can be played.[100%] 4.Debug music files can be opened from the media center, but can’t be played in CN platform.[0%->30%] 5.Debug Seek Functionality is not working for MPEG PS files(Frozen video was seen after seek)[0%->30%] 6.GraphicBufferAllocator fail for dream APP.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(January.03 to January.09)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [85%->pendding] 2.Server Maintenance.[100%] 3.Debug music files can be opened from the media center, but can’t be played in CN platform.[100%] 4.Debug Seek Functionality is not working for MPEG PS files(Frozen video was seen after seek)[100%] 5.Debug Memory audio is not playing as required.[0%->30%] | xiangbin.feng | On schedule |  |  |  |  | 1
(January.12 to January.17)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study and conclude the git-related knowledge. [85%->pendding] 2.Server Maintenance.[100%] 3.Debug Memory audio is not playing as required.[100%] 4.Debug Video playback is not smooth for specific MPEG-PS file through DLNA.[100%] 5.Debug Music playback screen is not getting timed out after applying seek till the EOF for mp3 files.[0%->80%] | xiangbin.feng | On schedule |  |  |  |  | 1
(January.19 to January.24)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Debug Music playback screen is not getting timed out after applying seek till the EOF for mp3 files.[80%->100%] 2.Server Maintenance.[100%] 3.Debug Demo video jerk is observed during the demo video playback.[60%] 4.Debug Playback some video have not smooth of media mode.[100%] 5.Debug Video play back stopped after few seconds for Antenna play App.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(January.26 to January.30)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Debug Demo video jerk is observed during the demo video playback.[60%->100%] 2.Server Maintenance.[100%] 3.Discuss memory audio issue with TPVision, I have offered the solution to TPVison, they will do some sanity check and confirm.[60%] 4.Debug Junk value is shown for start duration for few seconds and junk audio is heard while trying to play .wmv file .[50%] | xiangbin.feng | On schedule |  |  |  |  | 1
(February.02 to February.07)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Analyze the root cause for the delay in flush complete event which may cause the reset timeout.[50%] 2.Server Maintenance.[100%] 3.Participate in the group training for mediaplayer.[100%] 4.Discuss memory audio issue with TPVision, I have offered the solution to TPVison, they will do some sanity check and confirm.[60%->80%] 5.Debug Junk value is shown for start duration for few seconds and junk audio is heard while trying to play .wmv file .[50%->100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(February.09 to February.15)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Analyze the root cause for the delay in flush complete event which may cause the reset timeout.[50%->100%] 2.Server Maintenance.[100%] 3.Discuss memory audio issue with TPVision, I have offered the solution to TPVison, they will do some sanity check and confirm.[80%->90%] 4.Analyze the issue that frames are going very fast for few seconds on applying FR seek for file 000007 issue.[70%] | xiangbin.feng | On schedule |  |  |  |  | 1
(February.25 to February.28)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Review theora ogg knowledge.[100%] 2.Server Maintenance.[100%] 3.Discuss memory audio issue with TPVision, I have offered the solution to TPVison, they will do some sanity check and confirm.[90%->100%] 4.Analyze the issue that frames are going very fast for few seconds on applying FR seek for file 000007 issue.[70%-80%] | xiangbin.feng | On schedule |  |  |  |  | 1
(March.02 to March.06)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Analyze the crash issue on Sony platform[70%] 2.Server Maintenance.[100%] 3.analyze TF515PHIALLMTK01-6870 which is related to clock state after seek.[50%] 4.Analyze the issue that frames are going very fast for few seconds on applying FR seek for file 000007 issue.[80%-100%] 5.Urge and help the crew to analyze the related bugs together.[30%] | xiangbin.feng | On schedule |  |  |  |  | 1
(March.09 to March.13)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Analyze the crash issue on Sony platform[70%-100%] 2.Server Maintenance.[100%] 3.analyze TF515PHIALLMTK01-6870 which is related to clock state after seek.[50%->100%] 4.Urge and help the crew to analyze the related bugs together.[30%->100%] 5.Analyze the TF515PHIALLMTK01-4327 PR that 3d video not deteced when video with signaling is played through usb/DLNA[100%] 6.Analyze the PR(TF515PHIALLMTK01-8825) that Multiple issues seen on while plaback of specific WMV file through Harddisc.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(March.16 to March.20)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Debug PR(TF515PHIALLMTK01-4942) that after applying pause video is not playing for the specific mp4 file through DLNA [100%] 2.Server Maintenance.[100%] 3.Have a meeting with Song.Wang and Yinyin.Zhang to review the bug list and discuss the priority for each one[100%] 4.Debug PR(TF515PHIALLMTK01-5350) that file can not be read or found message seen and TV will reboot after do "move next" in USB-Video mode.[100%] 5.Debug PR(TF515PHIALLMTK01-8668) that Playback is not getting initated, when perform back to back playback[100%] 6.Debug PR(TF515PHIALLMTK01-8997) that On applying trickmode till end of the file, press play button, the playback not getting initiated.[100%] 7.Debug the PR(TF515PHIALLMTK01-10209) that inconsistence behavior for video file playback through USB on U+ board.[50%] | xiangbin.feng | On schedule |  |  |  |  | 1
(March.23 to March.27)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Debug PR(TF515PHIALLMTK01-5387) that file struck during the playback. [100%] 2.Server Maintenance.[100%] 3.Debug PR(TF515PHIALLMTK01-11508) that A/V freezes is seen during content browser playback[100%] 4.Debug PR(TF515PHIALLMTK01-11900) that to play ARD mediathek video, video has flash.[100%] 5.Debug PR(TF515PHIALLMTK01-10209) that inconsistence behavior for video file playback through USB on U+ board.[50%->100%] 6.Debug PR(TF515PHIALLMTK01-11081) that BBC iplayer - playback stuck at 5 secs, and all black between 0~5s.[100%] 7.Debug PR(TF515PHIALLMTK01-8891) that audio loss and playback stops for specific WMA_Pro file after multiple seek.[100%] 8.Debug PR(TF515PHIALLMTK01-12084) that constrained Baseline Profile Files are not playing through USB.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(March.30 to April.03)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Debug PR(TF515PHIALLMTK01-11113) that watch Demo me, TV reboot. [100%] 2.Server Maintenance.[100%] 3.Trace the WMA-Pro parse module and check the WMA-Pro head information which is sent to driver.[100%] 4.Futher analyze that file struck during the playback, sync this issue with MTK.[100%] 5.Analyze the MooPlayer crash issue while integrating code.[100%] 6.Debug PR(TF515PHIALLMTK01-12357) that DTS wav files not playing.[30%] | xiangbin.feng | On schedule |  |  |  |  | 1
(April.07 to April.10)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Learn basic knowledge of EXOplayer and EXOplayer Demo.[50%] 2.Server Maintenance.[100%] 3.Help to add some code to aud_drv.c and analyze the TF515PHIALLMTK01-8891 PR.[100%] 4.Debug PR(TF515PHIALLMTK01-12357) that DTS wav files not playing.[30%->100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(April.20 to April.24)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1..Debug PR(TF515PHIALLMTK01-13357) that DTS wav files not playing.[100%] 2.Server Maintenance.[100%] 3.Debug PR(TF515PHIALLMTK01-13714) that movie playback freeze on after 51:49 minutes Playback and No AV present when switch to tuner.[100%] 4.Debug PR(TF515PHIALLMTK01-14260) that browser video to TV, TV reboot.[100%] 5.Trace the flow of ExoPlayer prepare(). [60%] | xiangbin.feng | On schedule |  |  |  |  | 1
(May.04 to May.08)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Debug PR(TF515PHIALLMTK01-14741) that Browser video to TV, TV black screen.[100%] 2.Server Maintenance.[100%] 3.Debug PR(TF515PHIALLMTK01-12084) that Constrained Baseline Profile Files are not playing through USB.[100%] 4.Trace the flow of ExoPlayer prepare(). [60%->100%] 5.study dequeue/queue buffer of MediaCodec.[20%] | xiangbin.feng | On schedule |  |  |  |  | 1
(May.11 to May.15)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Debug TF515PHIALLMTK01-15747 that 3D format AVC and AC-3 shows the format not supported.[100%] 2.Server Maintenance.[100%] 3.Study the knowledge of WAV file format and write the related document.[20%] 4.Study Git knowledge and do some work. [50%] 5.study dequeue/queue buffer of MediaCodec.[20%->50%] 6.Help to reproduce TF515PHIALLMTK01-15109 that TV shown blank screen while image or video playback after youtube playback followed by AV lost on tuner.[50%] | xiangbin.feng | On schedule |  |  |  |  | 1
(May.18 to May.22)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Study the structure of ContentBroswer, and the relation among activities.[30%] 2.Server Maintenance.[100%] 3.Study the knowledge of WAV file format and write the related document.[20%->60%] 4.study dequeue/queue buffer of MediaCodec.[50%->100%] 5.Trace the create flow of Extractor.[100%] 6.Debug TF515PHIALLMTK01-15840 that Some video picture will flash and no audio output.[100%] 7.Help to reproduce TF515PHIALLMTK01-15109 that TV shown blank screen while image or video playback after youtube playback followed by AV lost on tuner.[50%->100%] | xiangbin.feng | On schedule |  |  |  |  | 1
(May.25 to May.29)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | fix CRs /Review MooPlayer | fix CRs /Review MooPlayer | 1.Debug PR(TF515PHIALLMTK01-9585) that MT5593T USB can not playback HEVC FHD and UHD clips.[100%] 2.Server Maintenance.[100%] 3.Study the knowledge of WAV file format and write the related document.[60%->pending] 4.With ExoPlayer integration requires, Analyze the interfaces of TvMediaPlayer.java and write the related document.[100%] 5.Discuss the interface design of ExoPlayer and how to push code.[100%] | xiangbin.feng | On schedule |  |  |  |  | 1