## Weekly report
(May.25 to May.29)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer study | Mooplayer OMX debug and EXOplayer study | 1. Debug [TF515PHIALLMTK01-16235(360852)] [CB] Most of the time ANR(media is not responding) is seen during CB playback and after that file cannot be read OSD is seen for any file playback. [Root Cause] In the multi-time playback,when end the playback of TS file,the vdec resource isn't release! [Solution] Has passed to the team of tsplayer to solve the issue.[100%] 2.Debug [TF515PHIALLMTK01-16093(359803)] [U+] Most of the time target crashes for the video playback. [Root Cause] According the log , it find that the audio compnent not shutdown in the previous playback . [Status] Wait for the available U+ device to analyze in the furture. [40%] 3. Write the outline about ExoPlayer Library.[100%] 4.Learn the interface of ExoPlayer for ContextExplorer.[20%-40%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(June.1 to June.5)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer Wrap | Mooplayer OMX debug and EXOplayer Wrap | 1.Debug [TF515PHIALLMTK01-16093(359803)] [U+] Most of the time target crashes for the video playback. [Root Cause] According the log , it find that the audio compnent not shutdown in the previous playback . [Status] Wait for the available U+ device to analyze in the furture. [40%] 2. Wrap the HLS interface about Exoplayer,set up the HLS test server.[60%] 3.Learn the interface of ExoPlayer for ContextExplorer.[40%-50%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(June.8 to June.12)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer Wrap | Mooplayer OMX debug and EXOplayer Wrap | 1.Debug [TF515PHIALLMTK01-16093(359803)] [U+] Most of the time target crashes for the video playback. [Root Cause] According the log , it find that the audio compnent not shutdown in the previous playback . [Status] Wait for the available U+ device to analyze in the furture. [40%] 2.Debug [TF515PHIALLMTK01-17356(365708)] [BBC][Catal][Regression]HLS Playback is not always restored after buffering [Status] On the version QM152E_R0.3.237.0,i can't reproduce the issue(30times),has passed to cofirm. [80%] 3. Wrap the HLS interface about Exoplayer,set up the HLS test server.[90%] 4.Learn the interface of ExoPlayer for ContextExplorer.[50%-55%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(June.15 to June.19)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer Wrap | Mooplayer OMX debug and EXOplayer Wrap | 1.Debug [TF515PHIALLMTK01-16093(359803)] [U+] Most of the time target crashes for the video playback. [Root Cause] According the log , it find that the audio compnent not shutdown in the previous playback . [Status] On the latest version,it didn't happend. Close. [100%] 2.Debug [TF515PHIALLMTK01-17120(364581)] [PTA][iOS][CB] Video Playback is not proper for Time laps Video. [Status] On the version QM152E_R0.3.245.0,i can't reproduce the issue,has passed to cofirm. [80%] 3.Learn the draft about HLS,prepare the PPT and share it.[100%] 4.Learn the interface of ExoPlayer for ContextExplorer.[50%-55%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(June.22 to June.26)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer Wrap | Mooplayer OMX debug and EXOplayer Wrap | 1.Debug [TF515PHIALLMTK01-17120(364581)] [PTA][iOS][CB] Video Playback is not proper for Time laps Video. [Status] On the version QM152E_R0.3.245.0,i can't reproduce the issue,has passed to cofirm. [80%] 2.Modify the hls section part of Exoplayer, simply the interface of hlswraper.[100%] 3.Learn the interface of ExoPlayer for ContextExplorer.[55%-60%] 4.Test the DLNA section of Masf2K16 and check the logcat log about DMP.Fix the section of DMP about Masf with Hyman, track the codes to future analyze.[20%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(June.29 to July.3)
project | type | project stage |  | D | Function owner | status | Development stage |  | risk
|  | current | next |  |  |  | current | next
2k15 EU Android | A | Mooplayer OMX debug and EXOplayer Wrap | Mooplayer OMX debug and EXOplayer Wrap | 1.Debug [TF515PHIALLMTK01-17120(364581)] [PTA][iOS][CB] Video Playback is not proper for Time laps Video. [Status] On the version QM152E_R0.5.1.0,i can't reproduce the issue,wait to update state. [80%] 2.Learn the interface of ExoPlayer for ContextExplorer.[60%-65%] 3.Test the DLNA section of Masf2K16 and check the logcat log about DMP.Fix the section of DMP about Masf, track the dmr about break in problem.[20%-70%] | Xueyi.Chen | On schedule | implement and debug(With Schedule) | implement and dubug ( next Week )
(July.6 to July.10)
No. | item | status | Highlight | comment
1 | PR: [TF515PHIALLMTK01-17120(364581)] [PTA][iOS][CB] Video Playback is not proper for Time laps Video. | Debug the issue,On the version QM152E_R0.5.1.0,can't reproduce the issue,has passed to QA to confirm. | Wait for the QA reply.
2 | DLNA function about 2K16MASF FB2 . | 1.Fix the DMP can't play issue from apk layer instead of framework layer.on R0.0.20.0,DMR and DMP is work normal. 2.Check the MRC about DLNA function
3 | Exoplayer Study. | 1.Review the code about exoplayer demo. 2.Learn the exoplayer impletement
(July.13 to July.17)
No. | item | status | Highlight | comment
1 | PR: [TF515PHIALLMTK01-17120(364581)] [PTA][iOS][CB] Video Playback is not proper for Time laps Video. | Debug the issue,On the version QM152E_R0.5.11.0,the reason is the mooplayer can't acquire the data from the source.
2 | DLNA function about 2K16MASF FB2 . | 1.Track the DLNA certification tool MVCT failed log.The reson is the exactor could not be created right. 2.Check the MRC about DLNA function codes.it can't work due the Ts can't playback.