## Weekly report(WK49)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
|  | 2015/6/29-2015/7/3 | week 27
2k15 EU Android | A | 1. Learn about content explorer of DLNA. 2. fix the pr PRTF515PHIALLMTK01-19038 3. fix the PR TF515PHIALLMTK01-18438 4. fix the PR TF515PHIALLMTK01-18302 | 1. Fix the PR 2. Read the code of ExoPlayer lib. | 1. Learn about the content expoler code of MainActivity about DLNA[90%->92%] 2. Learn about Git of git fetch/git rebase/git reset [70%->75%] 3. Help check the PR: TF515PHIALLMTK01-18302 , normal playback, audtimes from 30367999 jump to 0. may be file broken. Need TPVision check[100%] 4. Fix the PR: TF515PHIALLMTK01-18483,audio is less than video, then seek, video mute. After seek, hardwareclock will wait AudioReady, then Aout. But now audio send EOS, [100%] 5. Set up the U+ board, build the sing2/sing0 code. Check the pr PRTF515PHIALLMTK01-19038. About 17903245 alway send data, may be driver not decoder. Need further nal. But now U+ can't be lighted [40%%] | Xianmei Liao | On schedule |  |  |  |  | 1