## Weekly report(WK49)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
2k15 EU Android | A | 1. Study mp4_midxbuld 2. study Stagefright | Study Stagefright | 1. study mp4_midxbuld(key table bulid/ midxbuld indexing and so on) [done: 60%] 1. study setDataSource function from APP level to AwsomePlayer level[done:90%] | Xianmei Liao | On schedule |  |  |  |  | 1
2013/12/9 - 2013/12/13
| A | 1. Study MPEG4Extractor 2. Study media player processes | Study Stagefright MPEGTSExtractor | 1. study MPEG4Extractor included: recognize/parsechunk/sampleTable/sampleIterator [done: 90%] 1. study Media player processes from Mediaplayer.java to AwsomePlayer.cpp [done:85%] | Xianmei Liao | On schedule
2013/12/16-2013/12/20
| A | 1. Study MPEG4Extractor 2. Study MPEGTSExtractor 3. OpenMax | Study MPEGTSExtractor OpenMax | 1. study MPEG4Extractor included: summarize and organize documents [done: 90%] 2. study MPEGTSExtractor include: recognize the file, ATSParser[done:65%] 3. preliminary understanding OpenMax [done:50%] | Xianmei Liao | On schedule
2013/12/23-2013/12/27
|  | 1. Study MPEG4Extractor 2. Study MPEGTSExtractor 3. Study MediaPlayerService | Add API Study MPEG4Extractor MediaPlayerService framework | 1. Help other group to solute the MP4 bug and study MPEG4Extractor [done: 75%] 2. continue to study MPEGTSExtractor include: MPEGTSSniff fuction, ATSParser, program, stream[done:30%] 3. Study the mediaplayerService framework [done:60%] | Xianmei Liao | On schedule
2013/12/29-2014/1/2
|  | 1. Add a new API 2. TsPlayer 3. MooPlayer | Study MooPlayer | 1. Add a new API from JAVA level to AwesomePlayer [done: 85%] 2. study TsPlayer init /TvPlayerService / UriParser / UcPlayerBase[done:70%] 3. Study MooPlayer AHandler/ ALooper [done:20%]
|  | 2014/1/ -2014/1/10 | week 2
2k15 EU Android | A | 1. Study MooPlayer 2. Study TimedText 3. Study Smooth Streaming | Study smooth streaming and timedtext | 1. Study setDataSource and PrepareAsyn and read of TimedText [done: 95%] 2. study basic knowledge of Smooth Streaming and build a IIS platform, Study setDataSource and prepareAsyn of Smooth Streaming [done:85%] 3. Participate the training of our group and study RM/OMX class Diagram [done:40%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/1/13 - 2014/1/18 | week 3
2k15 EU Android | A | 1. Study Smooth Streaming flow 2. study Smooth Streaming spec | Play Smooth Streaming and MP4 | 1. Stydy Smooth Streaming spec inlude ism, ismc file and Read Smooth streaming parse code[done: 95%] 2. Study setDataSource , prepareAsyn and start of Smooth Streaming in JAVA layer[done:100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/1/20- 2014/1/24 | week4
2k15 EU Android | A | 1. Collate documents of Smooth Streaming 2. Collate documents of MPEG4Extractor | Test Smooth Streaming and MP4 | 1. Collate documents of Smooth Streaming include drawing flow diagram, reading spec and code[done: 100%] 2. Collate documents of MPEG4Extractor include flow of setDataSource, prepare.[done:60%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/2/9-2014/2/14 | week7
2k15 EU Android | A | 1. check mp4 bug 2. study android apk | study apk fixs CRs | 1. read MP4Extractor code then add log, find the bug[done: 90%] 2. study to write a sample demo of media player.[done:70%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/2/16-2014/2/21 | week8
2k15 EU Android | A | 1. study android apk | study apk | 1. study basic knowledge of android, relative layout file, activity, and listview, and write a simple palyer[done: 100%] 2. write a simple player for playing smoothstreaming, and try to fix the bug. Then read GtvVideoViewTest.java code [done:65%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/2/23-2014/2/28 | week9
2k15 EU Android | A | 1. Study apk/add log 2. MPEG4Extractor test | 1.unit test/ fix SmoothStreaming CRs 2. unit test/fix MPEGExtractor | 1. play SmoothStreaming (java) use my apk and add some log to try fix the bug [done: 65%] 2. add log and build MPEG4Extractor and find some problem: it parse not finish but can read data ok[done:35%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/3/1-2014/3/7 | week10
2k15 EU Android | A | 1. unit test/fix MPEG4Extractor 2. test/fix SmoothStreaming | 1.unit test/ fix SmoothStreaming CRs 2. unit test/fix MPEGExtractor | 1. add log and test smoothstreaming in the FW3_3 demo [done: 40%] 2. add log and build MPEG4Extractor and fix some problem: ctts box and esds box parse, but the audio still not play[done:60%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/3/10-2014/3/14 | week11
2k15 EU Android | A | 1. unit test/fix MPEG4Extractor 2. study OMX | 1.unit test/ fix SmoothStreaming CRs 2. unit test/fix MPEGExtractor | 1. study esds and mp4a box, and then ADTS header structor [done: 100%] 2. add log and build MPEG4Extractor and try to fix the problem of audio can't play[done:40%] 3. learn prpare flow of AOMXComponent[done:50%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/3/17-2014/3/23 | week12
2k15 EU Android | A | 1. unit test/fix FFmpegExtractor | 1.unit test/ fix MediaExtractor 2. unit test/fix FFmpegExtractor | 1. test mp4 file use FFmpegExtractor [done: 100%] 2. review mov_probe、mov_header function and add log to test mp4 file[done:70%] 3. study the architecture of ffmpeg and probe flow[done:80%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/3/23-2014/3/28 | week13
2k15 EU Android | A | 1. unit test/fix FFmpegExtractor | 1.unit test/ fix MediaExtractor 2. unit test/fix FFmpegExtractor | 1. review contractor of MOVContext\AVIOContext\AVFormatContext [done: 100%] 2. review mov_header function and add log to test mp4 file[done:50%] 3. study timedText and review code[done:60%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/4/1-2014/4/4 | week14
2k15 EU Android | A | 1. unit test/fix FFmpegExtractor 2.study mov | 1.study smoothstreaming 2. study timedtext | 1. study MP4 spec and MP4Extractor, then do a report abort them [done: 100%] 2. study mov_probe/mov_read_header/mov_read_packet, then write the document[done:100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/4/7-2014/4/11 | week15
2k15 EU Android | A | 1. study SmoothStreaming 2.study TimedText | 1.test smoothstreaming 2. test timedtext | 1. study SmoothStreaming.java and SmoothStreaming.cpp then write ppt about them [done: 80%] 2. study TimedText then write ppt[done:90%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/4/14-2014/4/18 | week16
2k15 EU Android | A | 1. fix CRs of SmoothStreaming 2.fix CRs ofTimedText | 1. fix CRx of smoothstreaming 2. Study TTML/3GPP timedText | 1. try to fix the bug of timedtext, find get->currentposition is a nagtive value [done: 50%] 2. study SmoothStreaming(SmoothStreamingSession.cpp / AFragmentMP4Parse/ISMParse)and try fix the bug, found the position.[done:70%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/4/21-2014/4/25 | week17
2k15 EU Android | A | 1. fix CRs of SmoothStreaming 2.fix CRs ofTimedText | 1. fix CRx of smoothstreaming 2. Study timedText and write document | 1. study in band of timedtext and draw flowcharts about them, explored related issues with gengsheng.Li[done: 80%] 2. study SmoothStreaming(SmoothStreamingSession.cpp /DownloadQueue.cpp )and found the bug position to fix it.[done:70%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/4/28-2014/4/30 | week18
2k15 EU Android | A | 1. study seek 2.write document about timedtext | 1. fix CRx of smoothstreaming 2. Study seek | 1. study seek flow and test it[done: 50%] 2. write a English document about timedtext.[done:100%] 3. study code about how to build index table of avi format .[done:50%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/5/5-2014/5/9 | week19
2k15 EU Android | A | 1.merge marvell code to MTK 2.write document about MooPlayerSource | 1. fix CRx of tag45 | 1. merge marvell code to tag45 [done: 100%] 2. write a English document about MooPlayerSource.[done:90%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/5/12-2014/5/16 | week20
2k15 EU Android | A | 1. fix CRx of tag45 2. study asf | 1. study mkv/flv/ts/avi | 1.fix the bug of tag45 which can't play smoothly after merge marvell code [done: 30%] 2.review the mediaplayer and mooplayer code, study Binder.[done:80%] 2.study the asf spec and read asf code.[done:80%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/5/22-2014/5/30 | week22
2k15 EU Android | A | 1. study spec of OMX 2. study OMX | 1. Fix bugs of MooPlayer after stop can't play the video | 1.Study the spec of OMX [done:70%] 1.follow the flow of prepare, read related code about AOMXComponent/AOMXProxy [done:90%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/6/3-2014/6/6 | week23
2k15 EU Android | A | 1. Test mp4/subtitle/Smoothstreaming and report bugs 2. Fix bugs for smoothstreaming | 1. Fix bugs for smoothstreaming | 1.Test mp4/subtitle/Smoothstreaming and report bugs [done:100%] 1.Fix bugs for smoothstreaming [done:5%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/6/9-2014/6/13 | week24
2k15 EU Android | A | 1. Fix bugs for smoothstreaming | 1. Fix bugs for smoothstreaming | 1.Fix the bugs of smoothstreaming not suport WAM formate[done:60%] 2.Check the bug that could't open url with Chinese [done:50%] 3.Fix the bug of smoothstreaming can't play completely all of segment mp4[done:10%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/6/16-2014/6/20 | week25
2k15 EU Android | A | 1. Fix bugs for smoothstreaming and test timedtext | 1. Fix the bug of timedtext | 1.Fix the bug of smoothstreaming can't play completely all of segment mp4[done:100%] 2.Test Out of band timedtext and add the log in the flow[done:40%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/6/23-2014/6/27 | week26
2k15 EU Android | A | 1. Fix bugs for smoothstreaming and test timedtext and mp4 | 1. Fix the bug of timedtext and mp4 | 1.replace new so file, then smoothstreaming play OK[done:100%] 2.Fix the bug of SMI timedtext, because MediaPlayer.java not declared, but parse still not OK[done:50%] 3.Fix the bug of MP4 can't play HE-Av2 AAC decode[done:30%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/6/30-2014/7/4 | week27
2k15 EU Android | A | 1. Support PCM param 2. learn demo apk | 1.learn android apk 2. fix the bug of PCM | 1.learn android apk about: activity, intent, UI[done:100%] 2.add some code to support PCM[done:50%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/7/7-2014/7/11 | week28
2k15 EU Android | A | 1. Support PCM param 2. learn demo apk 3. review code of asf/mkv parse | 1.learn android apk 2.fix the bug of mp4 can't seek moretime | 1.learn android apk about: adapter/Thread/OnClickListener[done:70%] 2.add some code to support PCM[done:100%] 3.review the code of asf/mkv parse and relatived spec[done:75%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/7/14-2014/7/18 | week29
2k15 EU Android | A | 1. learn android apk 2. fix the bug of mp4 seek problem 3. test mp4/mpg/vob file, then fix bug | 1.learn android apk 2.fix the bug of mp4 can't seek moretime | 1.learn android apk about: Handle/Runnable mechanism, write code play media[done:100%] 2.test mp4/mpg/vob, then find the reason why can't play[done:100%] 3. fix the bug of mp4 seek to near the end,can't work well problem [done:10%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/7/21-2014/7/25 | week30
2k15 EU Android | A | 1.fix the bug of mp4 seek problem 2. write code of SSA source | 1.write code of ssa source 2.fix the bug of mp4 | 1.fix the bug of mp4 seek problem when play near the end of file[done:100%] 2.trace the flow of in band of subtitle, and then write the code of SSA Source, now read the source data ok, then write parse function[done:50%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/7/28-2014/8/1 | week31
2k15 EU Android | A | 1. fix the bug of ssasource 2. Discuss the problem of video/audio extension | 1.write code of out of band ssa source 2.write OMX_IndexExtAudioGetProfile and OMX_EVENT function | 1.Discuss the problem of OPEN.MAX.0 and OPEN.MAX.2 and arrangement the schdule[done:100%] 2.trace the flow of in band of subtitle, and then write the code of SSA Source write parse function, fix the bug of subtitles garbled and will not wrap problem[done:100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/8/4-2014/8/8 | week32
2k15 EU Android | A | 1. fix the bug of mp4 2. write OMX_IndexExtAudioGetProfile and OMX_EVENT function | 1.add some param of audio/video extension 2.write OMX_IndexExtAudioGetProfile and OMX_EVENT function | 1.write OMX_IndexProfile/level and the OMX_Event(IDECOD/VideoSolutionChanged) and dissuse with youming[done:70%] 2.check mooplayer support audio/video info and check the components, disscuss ra supported with xiangbin [done:100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/8/11-2014/8/15 | week33
2k15 EU Android | A | 1. merge marvel code to 2k15 2. write OMX_Indexe and OMX_EVENT function 3. add codec extension of RAW/FLAC/VORBIS/WMA | 1.fix the bug of play rtsp 2. review the code about audio codec extension | 1.write OMX_IndexProfile/level and the OMX_Event(IDECOD/VideoSolutionChanged) and dissuse with youming[done:100%] 2. add codec of RAW/FLAC/VORBIS/WMA[done:100%] 3. merge marvel code to 2k15, build success, build still have bug[70%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/8/17-2014/8/22 | week33
2k15 EU Android | A | 1. fix the bug of rtsp using nuplayer 2. fix the bug of apk in the Android_L | 1.fix the bug of play rtsp 2. fix the bug of paly video in the 5593 | 1.learn rtsp protocal and message header, track the process of nuplayer[done:100%] 2. analyzed the log of playing rtsp using nuplayer, feedDecoderInputData to dequeueAccessuint data in buffer, but can't empty buffer in Acodec of onInputBufferFilled[done:50%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/8/25-2014/8/29 | week34
2k15 EU Android | A | 1. fix the bug of rtsp using nuplayer 2. fix the bug of apk in the Android_L 3. add set/get config | 1.fix the bug of play rtsp 2. fix the bug of paly video in the 5593 | 1.flow the postFilleThisBuffer and emptyBuffer message, can't return EmptyBufferDone message, the bug to mtk[done:100%] 2. fix the apk can't back after playbackcomplete, but selectTrack still not work well[done:50%] 3. contact with mtk about a/v set/get profile&level and audio properties to set/get config[70%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/9/1-2014/9/5 | week35
2k15 EU Android | A | 1. fix the bug of rtsp using nuplayer 2. fix the bug of apk in the Android_L | 1.fix the bug of play rtsp 2. fix the bug of paly video in the 5593 3. fix the bug of apk when selectTrack | 1. fix the apk can't back after playbackcomplete, but selectTrack still not work well[50% -> pending] 2. contact with mtk about a/v set/get profile&level and audio properties to set/get config[70%-> pending] 3. fix the bug of rtsp SW4 [20% - > 85%] 4. porting a/v properties into new Android_l code then test mp4 file[100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/9/9-2014/9/13 | week36
2k15 EU Android | A | 1.fix the bug of play rtsp 2. fix the bug of paly video in the 5593 3. fix the bug of apk when selectTrack | 1.study DRM 2. maintaining the pak. 3. fix the bug of video | 1. fix the apk, which selectTrack still not work well[50% -> pending] 2. contact with mtk about a/v set/get profile&level and audio properties to set/get config[70%-> pending] 3. fix the bug of rtsp SW4 [85% - > 100%] 4. test wma/asf file from Zhenlu, then answer questions [100%] 5. fix the apk about modifed sdk path dialog and thumbnail[100%] 6. study DRM in android [65%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/9/15-2014/9/19 | week37
2k15 EU Android | A | 1. study DRM 2. git FB4.1 and build 3. merge omx_extension to MTK | 1. maintaining the pak. 2. fix the bug of video | 1. fix the apk, which selectTrack still not work well[50% -> pending] 2. contact with mtk about a/v set/get profile&level and audio properties to set/get config[70%-> pending] 3. study DRM in android [65%->80%] 4. git FB4.1 and build then test files, list codec support currently[100%] 5. merge and add OMX_extension in FB5 then release to MTK.[80%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/10/8-2014/10/11 | week38
2k15 EU Android | A | 1. init new code, build 2. contact Zhenlu about pcm | 1. maintaining the pak. 2. fix the bug of video | 1. fix the apk, which selectTrack still not work well[50% -> pending] 2.init new code, and build it. then test pcm codec, but still not work[100%] 3. study DRM in android [80%->pending] 4. contact Zhenlu about pcm[70%] | Xianmei Liao | On schedule |  |  |  |  | 1
2k15 EU Android | A | 1. init new code, build 2. contact Zhenlu about pcm | 1. maintaining the pak. 2. fix the bug of m4a\pcm 3. repo sync new code, and build | 1. fix the apk, add a TextView to show Log [80%] 2.init new code, and repo sync. Loaded the latest code and test file[100%] 3. 1、 Writing the latest pkg, then test m4a file, analyze log, update URTracker. [100%] 4. contact Zhenlu about pcm, and fix the bug[70%->100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/10/14-2014/10/17 | week39
2k15 EU Android | A | 1. support other group about to get codec 2. provide rtsp platform | 1. maintaining the pak. 2. fix the bug of m4a\pcm 3. repo sync new code, and build | 1. fix the apk, add a TextView to show Log [80%->pending] 2. review MediaPlayer.java and MediaFormat.java to get codec type, only get subtitle type, no audio/video interface[30%] 3. provided rtsp platform for demo[100%] 4. fix our apk demo, that can order to play video[70%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/11/10-2014/11/14 | week43
2k15 EU Android | A | 1. fix the bug of hevc/wmv/flac/flv/aiff | 1. fix a/v codec | 1. fix the bug of hevc, add hevc code, need add private data to pare[70%->75%] 2. fix the bug of aiff/sorenson/m4v[100%] 4. fix the bug of flac, it's mtk's issue[100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/11/17-2014/11/21 | week44
2k15 EU Android | A | 1. fix the bug of hevc/wmv/flac/avi/vorbis | 1. fix a/v codec | 1. fix the bug of hevc in mp4 file, add hevc code, need add start code in frame.[75%->100%] 2. fix the bug of DIVX3 in avi file. [100%] 3. fix the bug of VP8 in mp4/mkv file. [100%] 4. fix the bug of vorbis, add kKeyVorbisBooks info, but still can't play. may be mtk issue. [80%] 5. add wmv codec supported code, then test, release to mtk. [100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/11/24-2014/11/28 | week45
2k15 EU Android | A | 1. fix the bug of hevc/wmv/avi/vorbis | 1. fix a/v codec | 1. add wmv asf_header info and start code[80%] 2. repo init new code and merge build it [100%] 3. study git basic operation. [40%] 4. fix the bug of vorbis, add kKeyVorbisBooks info, but still can't play. may be mtk issue. [80%->pending] 5. add wmapro code to mtk, then fix the uncorrect paremeter. [80%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/12/1-2014/12/5 | week46
2k15 EU Android | A | 1. fix the bug of wmapro/videoproperty/3dformatchange | 1. go the hefei, review bug lists | 1. add the code about event: OMX_Event3DFormatChanged/OMX_EventVideoProperties info, then release to MTK[100%] 2.add wmv asf_header info and start code. then xiangbin to fix[80%->100%] 3. study git basic operation. [40%->pending] 4. add wmapro code to mtk, then fix the uncorrect paremeter. [80%->100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/12/8-2014/12/12 | week47
2k15 EU Android | A | 1. go to hefei, review bug lists and fix vorbis | 1. hefei, review bug lists and fix vorbis | 1. fix the codec of vorbis, need mtk to confirm what data need[10%] 2.Help check issue: TF515PHIALLMTK01-3134/ TF515PHIALLMTK01-1136/TF515PHIALLMTK01-1848 [60%] 3. Check the bug of hevc, which can't play audio, video play 5s. audio mtk only support aac-lc[100%] 4. Discuss the distribution of bug lists about((TF515PHIALLMTK01-1828/TF515PHIALLMTK01-1848) with yinyin. [70%] 5. check and test wmv/vc1 integration with yinyin.[100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/12/15-2014/12/19 | week1
2k15 EU Android | A | 1. hefei, review bug lists and fix vorbis | 1. fix vorbis codec 2. fix ambilight.mp4 bug | 1. fix the codec of vorbis, need mtk to confirm what data need[10%-60%] 2.Help check issue: ambilight.mp4 play 6 s, because we only send sample: 163, need mtk confirm, may be decoder error. [50%] 3. Disuss with yinyin about AV properties, updated the lists, then add some event/index in omx layer[80%] 4. Discuss the distribution of bug lists about((TF515PHIALLMTK01-1828/TF515PHIALLMTK01-1848) with yinyin. [70%-100%] 5.Help check issue: avi play not smoothly, may be pts value is not correct.[50%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2014/12/21-2014/12/26 | week2
2k15 EU Android | A | 1. AV properties 2. vorbis codec support | 1. AV properties 2. fix mp4 bug | 1. fix the codec of vorbis, need mtk to confirm what data need[60%-100%] 2.Help check issue: ambilight.mp4 play 6 s, because we only send sample: 163, need mtk confirm, may be decoder error. [pending, mtk processed] 3. Disuss with yinyin about AV properties, updated the lists, then add some event/index in omx layer[80-90%] 4. Help lisu check about .mp4 file return AV_STREAM_NOT_FOUND issue, because file height > 1080 [50%] 5.Help check issue: avi play not smoothly, may be pts value is not correct.[peding, to jianglong 50%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/1/4-2015/1/9 | week3
2k15 EU Android | A | 1. AV properties 2. resume/stop issue | 1. AV properties 2. DTS-HD resume issue 3. mpg pts/dts issue | 1. Help find AOMX block/crash issue after add aac profile only LC profile can through.[100% to Milind] 2.Add OMX_IndexConfigAudioBitrate to get audio bitrate info [100%] 3. Fix the bug of [TF515PHIALLMTK01-5624] Pause & Play is not working for DTS HD freezed, smilar to [TF515PHIALLMTK01-4942] .[100%] 4. Study build the paltform of DLNA and hbbtv, help xiangbin about FW5_Demo apk to check omx crash issue [30% to xiangbin] 5.check issue:[TF515PHIALLMTK01-4938], mpg get not correct pts/dts sometimes.[10%] 6. Help lisu check about .mp4 file return AV_STREAM_NOT_FOUND issue, because file height > 1080 [50%->close] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/1/12-2015/1/17 | week 4
2k15 EU Android | A | 1. DTS-HD resume issue 2. mpg pts/dts issue 3. study trick mode and MAT | 1. DTS-HD issue 2. BBCiPlayer issue 3. study trick mode and MAT | 1. check issue:[TF515PHIALLMTK01-4938], mpg get not correct pts/dts sometimes.[10%->100%] 2. Fix the bug of [TF515PHIALLMTK01-5624] Pause & Play is not working for DTS HD Video file through USB & first time applying seek Video freeze observed. [60%] 3. Fix the bug of [TF515PHIALLMTK01-4523] [CODEC]Play-pause from RC is not working for a file.The same 5642 .[100%] 4. Help check :[TF515PHIALLMTK01-1803] Video freeze is observed for few seconds while changing the audio language for MAT files through USB [100%] 5. Help check trick mode, then send data is iframe.[100%] 6. Study OMX in mooplayer, and the flow of trick mode and MAT. [70%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/1/12-2015/1/17 | week 4
2k15 EU Android | A | 1. DTS-HD issue 2. BBCiPlayer issue 3. study trick mode and MAT | 1. make auido/video format ppt 2. fix the mooplayer bug | 1. check issue:TF515PHIALLMTK01-5863] [BBCiPlayer-Certification Testing] When perform back to back playback, the audio/video is not coming, but subtitle data get displays. Waiting confirm[100%] 2. Fix the bug of [TF515PHIALLMTK01-5624] Pause & Play is not working for DTS HD Video file through USB & first time applying seek Video freeze observed. [60%->100%] 3. Help check :TF515PHIALLMTK01-6221] Media App is crashing when PlayAll is started using the RC_red key. The first frame is specific data, this is not need [100%] 4. Study OMX in mooplayer, and the flow of trick mode and MAT. [70%->pending] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/1/25-2015/1/29 | week 5
2k15 EU Android | A | 1. DTS-HD issue 2. BBCiPlayer issue 3. make audio video format ppt | 1. BBCiCatal/BBCiPlayer 2. fix the wmv pts/dts | 1. fix the bug of TF515PHIALLMTK01-6221Media App is crashing when PlayAll is started using the RC_red key. MPEG4 not need specific data[100%] 2. Check bug ofTF515PHIALLMTK01-5864 and TF515PHIALLMTK01-6578 . BBCiPlayer can play morining, but can't play afternoon. BBCiCatal can play OK.[100%] 3. Help check :TF515PHIALLMTK01-6754 SMTV][DASH+Playready]: Multiple issue seen when "Play Ready +mpeg dash Homemade 4 Marvell MPEG 4 HE-AAC" played, need playready key then test.[40%] 4. Study OMX in mooplayer, and the flow of trick mode and MAT. [70%->pending] | Xianmei Liao | On schedule |  |  |  |  | 1
2k15 EU Android | A | 1. file can not play 2. fix the wmv pts/dts 3. check crash issue |  | 1. fix the bug about wmv pts issue with xiangbin and test it[100%] 2. Check bug of TF515PHIALLMTK01-7794, after enalbe initiateSeek, then do flush, signalflush->sendCommand(kWhatFlush), it takes a long time, sometimes return notifyResetComplete, but sometimes not. Try to modified reset, after stop a long time.[50%] 3. Help check :TF515PHIALLMTK01-6754 SMTV][DASH+Playready]: Multiple issue seen when "Play Ready +mpeg dash Homemade 4 Marvell MPEG 4 HE-AAC" played, need playready key then test.[40%->pending] 4. Check the bug of TF515PHIALLMTK01-8263, need 3 mins, then can play. EmptyBuffer some data, then driver receive, but a momment, driver not receive the data, may be driver not decoder, "Decoder slow" in HardwareVideoDecoder.[50%] 4. Study OMX in mooplayer, and the flow of trick mode and MAT. [70%->pending] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/2/1-2015/2/7 | week 6
2k15 EU Android | A | 1. file can not play 2. fix the wmv pts/dts 3. check crash issue |  | 1. fix the bug about wmv pts issue with xiangbin and test it[100%] 2. Check bug of TF515PHIALLMTK01-7794, after enalbe initiateSeek, then do flush, signalflush->sendCommand(kWhatFlush), it takes a long time, sometimes return notifyResetComplete, but sometimes not. Try to modified reset, after stop a long time.[50%] 3. Help check :TF515PHIALLMTK01-6754 SMTV][DASH+Playready]: Multiple issue seen when "Play Ready +mpeg dash Homemade 4 Marvell MPEG 4 HE-AAC" played, need playready key then test.[40%->pending] 4. Check the bug of TF515PHIALLMTK01-8263, need 3 mins, then can play. EmptyBuffer some data, then driver receive, but a momment, driver not receive the data, may be driver not decoder, "Decoder slow" in HardwareVideoDecoder.[50%] 4. Study OMX in mooplayer, and the flow of trick mode and MAT. [70%->pending] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/3/16-2015/3/20 | week 12
2k15 EU Android | A | 1. TF515PHIALLMTK01-10081 2. fix the wmv pts/dts 3. check crash issue |  | 1. TF515PHIALLMTK01-10081,TF515PHIALLMTK01-10066, Analysize wmapro sample rate > 96000, There try 3 solution, MooPlayer notifyError, AOMXAudioDecoder/MtkAudioDecoder notify error, these have problem: after reset, still some resource not release.[50%] 2. TF515PHIALLMTK01-10878 close, check demome file format, but it play OK.[100%] 3. Help junchao in MTK fix the bug TF515PHIALLMTK01-5603, now getVideoProperties can get the value, get3Dproperty get the wrrog value, if map, will OK.[90%] 4. TF515PHIALLMTK01-8990, AAC profile(HE-AAC/LC) not support, ADTSHeader profile set uncorrect, after modified play OK, Athmananda will check again.[80%] 5. TF515PHIALLMTK01-5451, After resume, all component start, then send data to hadware layer to decoder. All the flow is true, BLR QA test 12 times OK. This PR had closed[100%] 6. TF515PHIALLMTK01-11126:select audio language multile times crash. Review the log, and follwing the flow of MAT, can't found anything. QA test about 50 times still OK, This PR had closed[100%] 7. TF515PHIALLMTK01-11888. TV has no AV and playback will be stopped on first 7s rot cause: pts:7520000, V/HardwareVideoDecoder( 985): ## Decode Slow always. vdec.q state = playing, MTK issue.[100%] 8. Help youmign anlysize file: 00147 file. after seek, PTS not correct. MooPlayer audTime is DTS, AOXComponent value is PTS, after modified, no audio/video jum still have. MTK to check. [100%] 4. Study OMX in mooplayer, and the flow of trick mode and MAT. [70%->pending] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/3/23-2015/3/27 | week 13
2k15 EU Android | A | 1. fix getvideoProperties/get3dproperty 2. Close the Demome/audio select/BBCiNew/shopDemome PR 3. analysize the 2DF issue 4. analysize the avi file pts and av sync issue | 1. inject wmapro sample rate >=96000 | 1. TF515PHIALLMTK01-10081,TF515PHIALLMTK01-10066, Analysize wmapro sample rate > 96000, There try 3 solution, MooPlayer notifyError, AOMXAudioDecoder/MtkAudioDecoder notify error, these have problem: after reset, still some resource not release.[50%->70%] 2. Help junchao in MTK fix the bug TF515PHIALLMTK01-5603, now getVideoProperties can get the value, get3Dproperty get the wrrog value, if map, will OK. WFR [90%->100%] 4. TF515PHIALLMTK01-8990, AAC profile(HE-AAC/LC) not support, ADTSHeader profile set uncorrect, after modified play OK, Athmananda will check again. Solving[80%->100%] 5. TF515PHIALLMTK01-12273/TF515PHIALLMTK01-9006/TF515PHIALLMTK01-12105/TF515PHIALLMTK01-11805. Play a avi file, pts invalid, av sync not property. WFR[100%] 6. TF515PHIALLMTK01-11888 to play 2DF video, no audio/video. Decoder Slow, MTK check is bandwidth issue.[100%] 7. TF515PHIALLMTK01-11959 Specific AVI file seek video hange. video I frame destroy. [100%] 8. TF515PHIALLMTK01-11982 Apple-HLS streaming not happens, the playback goes to freeze state after 5Secs. Decoder Slow. MTK check. [100%] 9. TF515PHIALLMTK01-8350 Audio heard first and then playback duration is updating for all audio files through USB. Audio Ready befor onResume. MTK fix. [100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/3/30-2015/4/3 | week 14
2k15 EU Android | A | 1. inject wmapro sample rate >=96000 2. Play mkv file, Decoder Slow! | 1. fix the bug: TF515PHIALLMTK01-12472 | 1. TF515PHIALLMTK01-10081,TF515PHIALLMTK01-10066, Analysize wmapro sample rate > 96000, There try 3 solution, MooPlayer notifyError, closed[70%->100%] 2. TF515PHIALLMTK01-8730, Multiple issues are observed for Specific MKV files through DLNA/USB Driver can’t decoder a sample data, so video hange after trick mode. To MTK[100%] 3. TF515PHIALLMTK01-11959, Specific AVI file is getting hang while applying seek in forward and backward direction. TPVision modified in MooPlayer that can send the second IFrame data to driver, But still can show the picture, only hav one Iframe, not B/P frame, can be push to show[100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/4/7-2015/4/10 | week 15
2k15 EU Android | A | 1. fix the bug: TF515PHIALLMTK01-12472 2. add audio implement of OMX_IndexConfig 3. Check the bug: TF515PHIALLMTK01-5387 4. study MediaExtractor and MediaCodec | 1. Study EXoPlayer and MediaExtractor 2. fix the bug | 1. help check the pr: TF515PHIALLMTK01-5387, STC junk problem, with the latest version and the patch received from MTK.[100%] 2. Checking the PR TF515PHIALLMTK01-8730, now file can play, but seek/trick not used, pause can be used, From the log: I/ASTAMooPlayer( 971): Source not seekable, TPVision fix the PR-51525 cause this issue, need TPVision to confirm. [100%] 3. add some code in AOMX for the bug: Get parameter Call are failing with error code -2147483648 [100%] 4. Study the MediaExtractor and MediaCodec some interface and application in android[10%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/4/13-2015/4/17 | week 16
2k15 EU Android | A | 1. fix the bug: TF515PHIALLMTK01-8730 2. Check the bug: TF515PHIALLMTK01-13114 3. study ExoPlayerDemo/MediaExtractor and MediaCodec | 1. Study EXoPlayer and MediaExtractor 2. fix the bug TF515PHIALLMTK01-13114 | 1. help check the pr:TF515PHIALLMTK01-13114.[Critical]when change the audio language ,the video will fastward for moment.[10%] 2. Re -checking the PR TF515PHIALLMTK01-8730, specific mkv file after trick, pause/play not used, From the log: V/OMX_MtkAudioDecoder( 970): audio timestamp:135946000, send many times, need MTK to further checking.[100%] 3. Study the ExoPlayerDemo, MediaExtractor and MediaCodec. Following the flow of ExoPlayerDemo and MediaCodec in Nativ[10%->30%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/4/20-2015/4/24 | week 17
2k15 EU Android | A | 1. Check the bug: TF515PHIALLMTK01-13114 2. study ExoPlayerDemo/MediaExtractor and MediaCodec | 1. Study EXoPlayer and MediaExtractor 2. fix bug | 1. help check the pr:TF515PHIALLMTK01-13114.[Critical]when change the audio language ,the video will fastward for moment. After seek, send the first video data, but the second data need wait about 50ms. Need further to MTK to check the AV sync not proper issue[10%->100%] 2. After navy modified the MediaExtractor to dlopen the FFmpegExtractor OK, NuMediaExtractor to call getMetaData return null. Because libasta_ffmpegextractor.so had been dlclosed. Need to modified. Now can go to FFmpegExtractor[100%] 3. Study the ExoPlayerDemo, MediaExtractor and MediaCodec. Following the flow of ExoPlayerDemo and MediaCodec in Nativ[30%->50%] 4. Test the audio/video currently support in ExoPlayer. [100%] | Xianmei Liao | On schedule |  |  |  |  | 1
|  | 2015/5/11-2015/5/15 | week 20
2k15 EU Android | A | 1. Write a apk for playing 3 mediaplayer 2. study ExoPlayerDemo/MediaExtractor and MediaCodec 3. Learn Git 4. fix the pr:14969 | 1. Study EXoPlayer and MediaExtractor 2. Learn Git 3. Write apk for mediaplayer switch | 1. Modified the Demo apk of John's then go into mooplayer, then switch one by one[100%] 2. Learn about Git[3%->10%] 3. Following the flow of ExoPlayerDemo. Learn ExoPlayerImpleInternal / sampleSource[55%->65%] 4. Close the PR:14969. Reproduce this PR about 10 times, but still can't reporduecd, then to Creator to confirm.[100%] 5. Read the code of MPEG4Extractor and OggExtractor.[50%] | Xianmei Liao | On schedule |  |  |  |  | 1