## Weekly report(WK49)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
|  | 2015/5/11-2015/5/15 | week 20
2k15 EU Android | A | 1. Write a apk for playing 3 mediaplayer 2. study ExoPlayerDemo/MediaExtractor and MediaCodec 3. Learn Git 4. fix the pr:14969 | 1. Study EXoPlayer and MediaExtractor 2. Learn Git 3. Write apk for mediaplayer switch | 1. Modified the Demo apk of John's then go into mooplayer, then switch one by one[100%] 2. Learn about Git[3%->10%] 3. Following the flow of ExoPlayerDemo. Learn ExoPlayerImpleInternal / sampleSource[55%->65%] 4. Close the PR:14969. Reproduce this PR about 10 times, but still can't reporduecd, then to Creator to confirm.[100%] 5. Read the code of MPEG4Extractor and OggExtractor.[50%] | Xianmei Liao | On schedule |  |  |  |  | 1