## Weekly report(WK49)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
|  | 2015/5/18-2015/5/23 | week 21
2k15 EU Android | A | 1. Check the PR 5603 2. study ExoPlayerDemo/MediaExtractor and MediaCodec 3. Learn Git 4. Learn about content browser | 1. Study EXoPlayer and MediaExtractor 2. Learn Git 3. Porting content expoler code to MSAF | 1. Learn about the content expoler code about how to go to VideoPlayerActivity, learn about android BrocastReceive and action[20%] 2. Learn about Git[10%->20%] 3. Learn about the latest ExoPlayerLib. Following the flow of ExoPlayerDemo. Learn ExoPlayerImpleInternal / sampleSource[65%->75%] 4. Check the PR 5603 in FHT board OK, but in U+ not OK, may be code difference between FHT and U+.[100%] 5. Read the code of MPEG4Extractor and OggExtractor.[50%->pending] | Xianmei Liao | On schedule |  |  |  |  | 1