## Weekly report(WK49)
project | type | project stage |  | Function | Function owner | status | Development stage |  | risk | highlight | manpower
|  | current | next |  |  |  | current | next
|  | 2015/5/25-2015/5/29 | week 22
2k15 EU Android | A | 1. Porting the content explorer to MSAF, build 2. Learn Git 3. Learn about content browser | 1. Write the interface of ExoPlayerAdapter 2. Learn Git 3. Learn about VideoPlayerActivity | 1. Learn about the content expoler code of VideoPlayerActivity, learn about android BrocastReceive and action[20%->50%] 2. Learn about Git[20%->40%] 3. Learn about the latest ExoPlayerLib. Following the flow of ExoPlayerDemo. Learn ExoPlayerImpleInternal / sampleSource[75%->85%] 4. Porting the content explorer to MSAF, fix the build error. Modified to MediaPlayer to play the media OK.[100%] | Xianmei Liao | On schedule |  |  |  |  | 1